## Cover
ASSESSMENT OF DRILLING AND GROUND SUPPORT
CONSUMABLE COSTS FOR UNDERGROUND DEVELOPMENT
Navachab Gold Mine Project, Byrnecut. May to August 2026.
STUDY DETAILS
Researcher | Irene Zinyetu Kavhura, student number 221315594
Programme | BSc Honours in Mining Engineering, University of Namibia
Department | Civil and Mining Engineering
Supervisor | Mr. Nekwaya Tuyeni Kelao
Development contractor | Byrnecut
Analysis period | May, June, July and August 2026
Currency | United States dollars, converted at the rate on the Inputs sheet
WHERE EACH OBJECTIVE IS ANSWERED
Objective | Sheet | Status
Objective 1: drilling consumable unit cost per metre | Unit_Cost section 2, C_Face_Drilling | Complete. Reported per metre advanced and per drilled metre.
Objective 2: ground support unit cost per metre, and the main cost drivers | Unit_Cost section 1, Pareto | Complete.
Objective 3: development productivity baseline | Advance section 2, DRM | Complete. Metres per month and per heading, and drilled metres per advance metre.
Objective 4: advance rate against total unit cost | Unit_Cost sections 3 to 5 | Complete. Equation 4 separates the consumption effect from the advance effect.
Analysis by heading and by portal | Portal_Analysis | Complete. All four months, with reconciliation checks.
Design compliance and over consumption | Plan_vs_Actual | Complete for bolts, split sets and mesh against the GSS standards.
CONTENTS
Equations | Every equation used, with its symbols defined
Inputs | Unit costs, exchange rate, design standards, portal split bases
Advance | Survey advance as recorded, and monthly totals
Consumption_PL | Stock counts as recorded, with consumption derived
A_Scaling | Scaling consumables
B_Ground_Support | Bolts, bearing plates and mesh
C_Face_Drilling | Shanks, bits, rods, couplings, centralisers, dollies
D_Cable_Bolting | Cable bolts and hardware
DRM | Drilled metres, and bit life for the 43 mm and 48 mm bits
Plan_vs_Actual | Design quantity against actual, by ground class
Unit_Cost | Equations 1 to 4, and why the unit cost moved
Portal_Analysis | Heading and portal results, with reconciliation checks
Pareto | Consumables ranked by cost contribution
Triangulation | The three mine consumption records reconciled
Charts | Figures 1 to 10
Daily_Log | Daily advance and installation record, 1 May to 24 August 2026
Daily_Tracker | Daily figures against the May to July baseline
Anomalies | Queries raised against the source data, and the action required
Data_Quality | Completeness and coverage of each source
How_to_Read | Symbols, formats and the numbered notes
READING THE WORKBOOK
Blue figures | Entered from a source document
Green figures | Drawn from another sheet
Black figures | Calculated
x | No unit price exists in the source data. Never treated as zero.
- | Cost already carried by another line
( ) | A negative figure, in the accounting convention
Shaded cells | Awaiting data, listed on the Anomalies sheet

## Dashboard
DASHBOARD
Whole underground mine, May to August 2026.
1 HEADLINE
Measure | Unit | May | June | July | August |  | Period
Development advance | m | 270.436 | 316.617 | 397.798 | 390.967 |  | 390.967
Ground support consumable cost | US$ | 377506.0684 | 298939.3483 | 385623.4037 | 327302.1911 |  | 327302.1911
Drilling consumable cost | US$ | 175938.32 | 164342.43 | 350729.41 | 294906.06 |  | 294906.06
Total consumable cost | US$ | 553444.3884 | 463281.7783 | 736352.8137 | 622208.2511 |  | 622208.2511
Total drilled metres | drilled m | 29381.1 | 33867 | 49347.6 | 42289.6 |  | 42289.6
Consumable cost per metre advanced | US$/m | 2046.4893 | 1463.2246 | 1851.0722 | 1591.4598 |  | 1591.4598
Consumable cost per drilled metre | US$/drilled m | 18.8367 | 13.6794 | 14.9218 | 14.713 |  | 14.713
Drilled metres per metre advanced | ratio | 108.6434 | 106.9652 | 124.0519 | 108.1667 |  | 108.1667
2 PORTAL AND GROUND CLASS
Portal | Ground | Metres, period | Share of metres |  |  |  | Ground support cost per metre
Northern Portal | All fair to poor, GSS_02 and GSS_03 | 756.39 | 54.98% |  |  |  | 1036.7869
Southern Portal | All good, GSS_01 | 619.428 | 45.02% |  |  |  | 976.9591
Portal and ground class coincide exactly in this data, so the two cannot be separated statistically.
3 WHERE THE MONEY IS
Consumable |  | Period cost | Share | Cumulative
1. MD bolt 2.4 m galvanised |  | 904575.3161 | 38.08% | 38.08%
2. Shank T45 RD520/525 D45 L525 |  | 473326.75 | 19.93% | 58.01%
3. Mesh 2.40 x 4.50 m galvanised |  | 353779.9267 | 14.89% | 72.9%
4. Bit adaptor T45F / T38M |  | 227125.95 | 9.562% | 82.47%
5. Coupling sleeve T45 / T38 |  | 100124.44 | 4.215% | 86.68%
4 DATA COMPLETENESS
Measure |  | Value |  |  |  | Meaning
Consumption captured by the issue registers |  | 0% | [5 empty] | The registers record about half of what the stock counts measure
Drilling items consumed but unpriced |  | 0 | [5 empty] | Each one shows x rather than zero
Material bought but not recorded as installed |  | 37.85% | [5 empty] | Stock count against LiveMine installation record

## Equations
EQUATIONS USED IN THIS MODEL
Every calculated figure in the workbook comes from one of the equations below.
Equation 1 Drilling consumable unit cost
UC drill = ( C bits + C rods + C shanks + C couplings + C centralisers ) ÷ m
UC drill | Drilling consumable unit cost, US$ per metre
C bits, C rods, C shanks, C couplings, C centralisers | Total cost of drill steel consumed in the period, US$. Consumption quantity from the stock reconciliation multiplied by the supplier unit price.
m | Total metres advanced in the same period, from the survey end of month report
Calculated on | Unit_Cost, and the item detail on C_Face_Drilling
Equation 2 Ground support consumable unit cost
UC support = ( C bolts + C mesh + C plates + C resin + C cable ) ÷ m
UC support | Ground support consumable unit cost, US$ per metre
C bolts, C mesh, C plates, C resin, C cable | Total cost of ground support consumed in the period, US$. Bearing plates are quoted inside the bolt price and are not costed separately.
m | Total metres advanced in the same period. Every development metre in this data receives support.
Calculated on | Unit_Cost, and the item detail on B_Ground_Support and D_Cable_Bolting
Equation 3 Total development unit cost
UC total = UC drill + UC support
UC total | Total consumable unit cost, US$ per metre
UC drill, UC support | Consumable unit costs from Equations 1 and 2, US$ per metre
Scope | Consumables only. Labour and equipment operating costs are outside the scope of this study and are not included in any figure in this workbook.
Calculated on | Unit_Cost
Equation 4 Change in unit cost between two periods
U1 − U0 = ( C1 − C0 ) ÷ A0 + C1 × ( 1/A1 − 1/A0 )
U0, U1 | Consumable unit cost in the earlier and later period, US$ per metre
C0, C1 | Total consumable cost in the earlier and later period, US$
A0, A1 | Metres advanced in the earlier and later period
first term | Consumption effect: the cost of using more or less material, holding advance constant
second term | Advance effect: the effect of spreading the same spend over a different number of metres
Calculated on | Unit_Cost, section 4
Equation 5 Pareto contribution
P i = C i ÷ Σ C i × 100 Cum i = Σ ( C 1 … C i ) ÷ Σ C i × 100
P i | Percentage contribution of consumable i to total consumable cost
C i | Total cost of consumable i in the period, with items ranked highest to lowest
Cum i | Cumulative percentage down the ranked list
Calculated on | Pareto
Equation 6 Currency conversion
Cost in US$ = Cost in N$ ÷ R
R | Exchange rate, Namibia dollars per United States dollar
Cost in N$ | Supplier unit cost as stated in the mine price list
Cost in US$ | The reporting currency of this workbook. Drilling prices are already quoted in United States dollars and are not converted.
Calculated on | Inputs, and every cost sheet
In any cost cell, x means that no unit price for that item exists in the source data. It is never treated as zero.

## Inputs
INPUTS AND ASSUMPTIONS
Unit costs, exchange rate, design standards and drilling geometry used throughout the workbook.
Blue figures are taken directly from a source document. Shaded cells are awaiting data; each one is listed on the Data_Quality sheet.
1 EXCHANGE RATE
Item | Description | Unit | Value
R | Namibia dollars per United States dollar | N$ / USD | 16.16
2 CONSUMABLE UNIT COSTS
Item code | Description | Unit | Unit cost (USD) | Unit cost (US$)
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 7.3845 | 119.3334
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 12.8972 | 208.4192
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 15.9311 | 257.447
BMG2024S | MD bolt 2.4 m galvanised | each | 65.8783 | 1064.5938
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 68.072 | 1100.0429
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 82.4854 | 1332.9642
3 CONVERSION FACTORS
Mesh sheet area | One sheet measures 2.40 m by 4.50 m | m2 | 10.8
Mesh rate | Galvanised mesh, price per square metre | USD / m2 | 7.6375
4 PORTAL SPLIT OF GROUND SUPPORT COST
Month | Northern Portal | Southern Portal |  | Basis
May 2026 | 39.67% | 60.33% |  | LiveMine installed quantities, measured by heading
June 2026 | 60.12% | 39.88% |  | LiveMine installed quantities, measured by heading
July 2026 | 66.19% | 33.81% |  | LiveMine installed quantities, measured by heading
August 2026 | 60.95% | 39.05% |  | Metres advanced. No LiveMine inventory extract was supplied for this month
See Notes sheet, note 1.
5 PORTAL SPLIT OF DRILLING CONSUMABLE COST
Month | Northern Portal | Southern Portal |  | Basis
May 2026 | 40.36% | 59.64% |  | Drilled metres, 8,398 north and 12,410 south
June 2026 | 56.31% | 43.69% |  | Drilled metres, 12,466 north and 9,671 south
July 2026 | 64.77% | 35.23% |  | Drilled metres, 20,928 north and 11,382 south
August 2026 | 64.3% | 35.7% |  | Drilled metres, 16,138 north and 8,961 south
See Notes sheet, note 2.
6 DRILLING CONSUMABLE UNIT COSTS
Item code | Description | Unit | Unit cost (US$)
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 308.1
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 5568.55
7335-4401 | Bit adaptor T45F / T38M | each | 4453.45
7314-6261 | Coupling sleeve T45 / T38 | each | 1925.47
7314-3652 | Coupling sleeve T38 / T38 | each | 69.96
7580-5243A-S70 | A340 43 mm button bit | each | 66.52
7580-5345A-R48 | A340 45 mm button bit | each | 78.93
7580-5148A-S81 | A340 48 mm TC button bit | each | 108.19
7580-4651A-S70 | A340 51 mm retrac bit | each | 94.13
7580-5602P-S70 | Reaming bit A340 102 mm | each | 343.33
7514-1664-S70 | T38 64 mm button bit | each | 136.44
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 79.73
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 498.85
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 639
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 439.59
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 317.43
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 184.75
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 276.63
M2000354 | Bolting centraliser dia 70 mm front | each | 45.12
M2000353 | Bolting centraliser dia 70 mm back | each | 68
M33191232 | Boring centraliser dia 48 mm | each | 61.09
33191231 | Boring centraliser dia 41 mm | each | 1884.83
33191232 | Boring centraliser dia 48 mm | each | 1733.67
33191234 | Bolting centraliser dia 66 mm guide | each | 1376.29
7979-2630 | T38 dolly 47 mm | each | 96.3
7979-2626 | T38 dolly 39 mm | each | 96.3
6 GROUND SUPPORT DESIGN STANDARD, MINIMUM QUANTITY PER CUT
Standard | Ground condition | MD bolt 2.4 m x 47 mm | Split set 2.4 m x 47 mm | Stubby split set 0.9 m x 39 mm | Mesh sheet 4.5 x 2.4 m | Source
GSS_01 | Good ground, Q >= 10 | 33 | 0 | 11 | 6 | GSS01 drawing, minimum quantity per cut
GSS_02 | Fair to poor ground, 10 > Q >= 4 | 15 | 18 | 11 | 6 | GSS02 drawing, minimum quantity per cut
GSS_03 | Poor ground, Q < 4 | 15 | 18 | 11 | 6 | GSS02 standard applied
7 DRILLING GEOMETRY, USED TO CALCULATE DRILLED METRES
Symbol | Description | Unit | Value
Cut length | Metres advanced per blast round | m | 4
Holes per face | Face holes drilled divided by rounds, from LiveMine | holes | 65.4
Hole length | Drilled length of each face hole, from LiveMine | m | 4.3
Bolt hole, MD bolt | Drilled length per MD bolt hole | m | 2.4
Bolt hole, split set 2.4m | Drilled length per 2.4 m split set hole | m | 2.4
Bolt hole, split set 0.9m | Drilled length per 0.9 m split set hole | m | 0.9
Bolt hole, cable bolt | Drilled length per cable bolt hole | m | 6.5

## Advance
SURVEY DEVELOPMENT ADVANCE
Source: Byrnecut Development Payment end of month reports, EOM Advance column, signed by the Byrnecut surveyor.
Ore and waste rows of one heading are consolidated. North Shoot Decline and NS_1040_ACC_N are one location.
1 ADVANCE AS RECORDED BY SURVEY
Month | Survey period | Heading as recorded | Location used in this model | Portal | Material | GS type | Profile (m2) | Advance (m)
May 2026 | 1 to 31 May 2026 | SOUTH DECLINE | South Decline | Southern Portal | Waste | GSS_01 | 31.12 | 75.154
May 2026 | 1 to 31 May 2026 | NORTH DECLINE | North Decline | Northern Portal | Waste | GSS_02 | 31.12 | 55.882
May 2026 | 1 to 31 May 2026 | MS_1040_ACC_waste | N_1040_ACCESS (NS 1040 access) | Northern Portal | Waste | GSS_02 | 31.12 | 6
May 2026 | 1 to 31 May 2026 | MS900_ACC_E | MS900_ACC_E | Southern Portal | Waste | GSS_01 | 31.12 | 17.508
May 2026 | 1 to 31 May 2026 | MS_1040_ACC_waste | N_1040_ACCESS (NS 1040 access) | Northern Portal | Waste | GSS_01 | 31.12 | 4.278
May 2026 | 1 to 31 May 2026 | MS900_DDR_N_waste | MS900_DDR_N | Southern Portal | Waste | GSS_01 | 31.12 | 22.683
May 2026 | 1 to 31 May 2026 | MS900_DDR_N_waste1 | MS900_DDR_N | Southern Portal | Waste | GSS_01 | 24.519 | 16.102
May 2026 | 1 to 31 May 2026 | S890_SP_W | S890_SP_W | Southern Portal | Waste | GSS_01 | 31.12 | 24.029
May 2026 | 1 to 31 May 2026 | S900_SMP W | S900_SMP_W | Southern Portal | Waste | GSS_01 | 24.519 | 5
May 2026 | 1 to 31 May 2026 | MS_1040_ACC_OD | N_1040_ACCESS (NS 1040 access) | Northern Portal | ORE | GSS_02 | 31.12 | 16.9
May 2026 | 1 to 31 May 2026 | MS900_DDR_N_OD | MS900_DDR_N | Southern Portal | ORE | GSS_01 | 24.519 | 26.9
June 2026 | 29 May to 28 June 2026 | SOUTH DECLINE | South Decline | Southern Portal | Waste | GSS_01 | 31.12 | 70.356
June 2026 | 29 May to 28 June 2026 | NORTH DECLINE | North Decline | Northern Portal | Waste | GSS_02 | 31.12 | 81.29
June 2026 | 29 May to 28 June 2026 | NS 1040 ACC_N | North Shoot Decline (NS_1040_ACC_N) | Northern Portal | Waste | GSS_02 | 31.12 | 71.538
June 2026 | 29 May to 28 June 2026 | NS_1040_SP_E | NS_1040_SP_E | Northern Portal | Waste | GSS_02 | 31.12 | 23.007
June 2026 | 29 May to 28 June 2026 | MS_0900_SP_S | MS_0900_SP_S | Southern Portal | Waste | GSS_01 | 31.12 | 19.667
June 2026 | 29 May to 28 June 2026 | MS_0900_RAD_E | MS_0900_RAD_E | Southern Portal | Waste | GSS_01 | 29.81 | 39.551
June 2026 | 29 May to 28 June 2026 | MS_0875_SMP_W | MS_0875_SMP_W | Southern Portal | Waste | GSS_01 | 24.558 | 11.208
July 2026 | 29 June to 28 July 2026 | SOUTH DECLINE | South Decline | Southern Portal | Waste | GSS_01 | 31.12 | 95.817
July 2026 | 29 June to 28 July 2026 | NORTH DECLINE | North Decline | Northern Portal | Waste | GSS_03 | 31.12 | 87.865
July 2026 | 29 June to 28 July 2026 | NORTH DECLINE_Waste | North Decline | Northern Portal | Waste | GSS_03 | 31.12 | 4.2
July 2026 | 29 June to 28 July 2026 | NS 1040 ACC_N | North Shoot Decline (NS_1040_ACC_N) | Northern Portal | Waste | GSS_03 | 31.12 | 96.63
July 2026 | 29 June to 28 July 2026 | NS_1040_LSP01_W | NS_1040_LSP01_W | Northern Portal | Waste | GSS_03 | 31.12 | 24.352
July 2026 | 29 June to 28 July 2026 | MS_0900_RAD_E | MS_0900_RAD_E | Southern Portal | Waste | GSS_01 | 29.81 | 17.112
July 2026 | 29 June to 28 July 2026 | MS_0870_DSP05_W | MS_0870_DSP05_W | Southern Portal | Waste | GSS_01 | 31.12 | 23.463
July 2026 | 29 June to 28 July 2026 | NS_1040_DSP02_W | NS_1040_DSP02_W | Northern Portal | Waste | GSS_02 | 31.12 | 25.788
July 2026 | 29 June to 28 July 2026 | MS_0900_SP_E | MS_0900_SP_E | Southern Portal | Waste | GSS_01 | 31.12 | 2.2
July 2026 | 29 June to 28 July 2026 | NORTH DECLINE_Ore | North Decline | Northern Portal | ORE | GSS_02 | 31.12 | 16.027
July 2026 | 29 June to 28 July 2026 | NS 1040 ACC_N_ore | North Shoot Decline (NS_1040_ACC_N) | Northern Portal | ORE | GSS_03 | 31.12 | 4.344
August 2026 | 29 July to 28 August 2026 | SOUTH DECLINE | South Decline | Southern Portal | Waste | GSS_01 | 31.12 | 66.894
August 2026 | 29 July to 28 August 2026 | MS_DSP06 | MS_DSP06 | Southern Portal | Waste | GSS_01 | 31.12 | 24.425
August 2026 | 29 July to 28 August 2026 | MS_PMP_STN1 | MS_PMP_STN1 | Southern Portal | Waste | GSS_01 | 29.81 | 16.689
August 2026 | 29 July to 28 August 2026 | MS_840_DSMP W | MS_840_DSMP W | Southern Portal | Waste | GSS_01 | 24.558 | 5.739
August 2026 | 29 July to 28 August 2026 | MS_900_RAD_E | MS_900_RAD_E | Southern Portal | Waste | GSS_01 | 29.81 | 32.861
August 2026 | 29 July to 28 August 2026 | MS_900_RAD_N | MS_900_RAD_N | Southern Portal | Waste | GSS_01 | 29.81 | 6.07
August 2026 | 29 July to 28 August 2026 | NORTH DECLINE | North Decline | Northern Portal | Waste | GSS_02 | 31.12 | 95.452
August 2026 | 29 July to 28 August 2026 | NS_1040_ACC_N | North Shoot Decline (NS_1040_ACC_N) | Northern Portal | Ore | GSS_02 | 31.12 | 31.787
August 2026 | 29 July to 28 August 2026 | NS_1020_ACC_W | NS_1020_ACC_W | Northern Portal | Waste | GSS_02 | 31.12 | 57.558
August 2026 | 29 July to 28 August 2026 | NS_1020_DSMP | NS_1020_DSMP | Northern Portal | Waste | GSS_02 | 24.558 | 10.505
August 2026 | 29 July to 28 August 2026 | NS_1020_LSP01 | NS_1020_LSP01 | Northern Portal | Waste | GSS_02 | 31.12 | 10.278
August 2026 | 29 July to 28 August 2026 | NS_1020_RAD_N | NS_1020_RAD_N | Northern Portal | Waste | GSS_02 | 29.81 | 32.709
2 MONTHLY TOTALS, WHOLE UNDERGROUND MINE
Measure | Unit |  | May 2026 | June 2026 | July 2026 | August 2026 | Period total |  | Mean per month
Days in period | days |  | 31 | 31 | 30 | 31
Total advance | m |  | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818 |  | 343.9545
Advance rate | m / day |  | 8.7237 | 10.2135 | 13.2599 | 12.6118 |  |  | 11.2022
Advance rate | m / shift |  | y | y | y | y
See Notes sheet, note 3.

## Consumption_PL
STOCK RECONCILIATION, MEASURED CONSUMPTION
Source: EOM PL Count Sheets for May and June 2026 and the End July EOM Stocktake Sheet.
Consumption = Opening count + Quantity received − Closing count. This measures material actually used, not material signed out of store.
|  |  | May 2026 |  |  |  | June 2026 |  |  |  | July 2026 |  |  |  | August 2026
Item code | Description | Unit | Opening (units) | Received (units) | Closing (units) | Consumption (units) | Opening (units) | Received (units) | Closing (units) | Consumption (units) | Opening (units) | Received (units) | Closing (units) | Consumption (units)
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | 75 | 0 | 68 | 7 | 68 |  | 67 | 1 | 67 | 5 | 71 | 1 | 71 | 72 | -1
7580-5243A-S70 | A340 43 mm button bit | each | 85 | 50 | 20 | 115 | 20 |  | 20 | 0 | 20 | 40 | 50 | 10 | 50 | 50 | 0
7580-5345A-R48 | A340 45 mm button bit | each | 330 | 0 | 258 | 72 | 258 |  | 258 | 0 | 258 |  | 248 | 10 | 248 | 223 | 25
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 26 | 0 | 25 | 1 | 25 |  | 20 | 5 | 20 | 45 | 20 | 45 | 20 | 19 | 1
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 3483 | 0 | 3300 | 183 | 3300 |  | 3123 | 177 | 3123 |  | 3380 | -257 | 3380 | 3300 | 80
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 3750 | 0 | 3450 | 300 | 3450 |  | 2921 | 529 | 2921 |  | 2520 | 401 | 2520 | 2200 | 320
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 888 | 0 | 145 | 743 | 145 | 4800 | 3996 | 949 | 3996 | 4800 | 6637 | 2159 | 6486 | 4200 | 2286
BMG2024S | MD bolt 2.4 m galvanised | each | 11095 | 0 | 8520 | 2575 | 8520 | 10080 | 14926 | 3674 | 14926 |  | 10763 | 4163 | 10279 | 6960 | 3319
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 3560 | 0 | 3560 | 0 | 3560 |  | 3545 | 15 | 3545 |  | 3545 | 0 | 3545 | 3336 | 209
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 4078 | 0 | 3438 | 640 | 3356 | 4800 | 7102 | 1054 | 7102 | 4800 | 9300 | 2602 | 9200 | 5970 | 3230
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 10560 | 0 | 7820 | 2740 | 7820 | 10080 | 15170 | 2730 | 15170 |  | 10680 | 4490 | 10638 | 6240 | 4398
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 2256 | 3675 | 3640 | 2291 | 3640 |  | 3232 | 408 | 3232 |  | 2411 | 821 | 2411 | 1642 | 769
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 15 | 50 | 57 | 8 | 57 | 60 | 98 | 19 | 98 | 45 | 109 | 34 | 109 | 85 | 24
7335-4401 | Bit adaptor T45F / T38M | each | 39 | 30 | 54 | 15 | 54 |  | 50 | 4 | 50 |  | 34 | 16 | 34 | 18 | 16
7314-6261 | Coupling sleeve T45 / T38 | each | 13 | 0 | 2 | 11 | 2 | 60 | 55 | 7 | 55 | 45 | 86 | 14 | 86 | 66 | 20
7314-3652 | Coupling sleeve T38 / T38 | each | 55 | 0 | 50 | 5 | 50 |  | 49 | 1 | 49 |  | 46 | 3 | 46 | 46 | 0
7580-5148A-S81 | A340 48 mm TC button bit | each | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 70 | 70 | 0 | 70 | 35 | 35
7580-4651A-S70 | A340 51 mm retrac bit | each | 30 | 0 | 20 | 10 | 20 |  | 5 | 15 | 5 | 20 | 15 | 10 | 15 | 0 | 15
7580-5602P-S70 | Reaming bit A340 102 mm | each | 38 | 0 | 24 | 14 | 24 |  | 22 | 2 | 22 | 15 | 23 | 14 | 23 | 11 | 12
7514-1664-S70 | T38 64 mm button bit | each | 3 | 40 | 21 | 22 | 21 |  | 1 | 20 | 1 | 20 | 20 | 1 | 20 | 8 | 12
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 70 | 100 | 108 | 62 | 108 |  | 66 | 42 | 66 | 70 | 116 | 20 | 116 | 46 | 70
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 27 | 0 | 26 | 1 | 26 |  | 26 | 0 | 26 |  | 19 | 7 | 19 | 0 | 19
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 202 | 0 | 187 | 15 | 187 |  | 169 | 18 | 169 | 35 | 188 | 16 | 187 | 163 | 24
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 59 | 0 | 57 | 2 | 57 |  | 56 | 1 | 56 |  | 53 | 3 | 53 | 49 | 4
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 36 | 0 | 21 | 15 | 21 |  | 9 | 12 | 9 |  | 9 | 0 | 9 | 5 | 4
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 7 | 0 | 7 | 0 | 7 |  | 3 | 4 | 3 | 5 | 7 | 1 | 7 | 6 | 1
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 6 | 0 | 6 | 0 | 6 |  | 5 | 1 | 5 | 5 | 9 | 1 | 9 | 8 | 1
M2000354 | Bolting centraliser dia 70 mm front | each |  | 0 | 48 | -48 | 48 |  | 39 | 9 | 39 | 60 | 87 | 12 | 87 | 83 | 4
M2000353 | Bolting centraliser dia 70 mm back | each | 26 | 0 | 60 | -34 | 60 |  | 60 | 0 | 60 | 60 | 118 | 2 | 118 | 117 | 1
M33191232 | Boring centraliser dia 48 mm | each |  | 0 | 48 | -48 | 48 |  | 48 | 0 | 48 | 50 | 94 | 4 | 94 | 92 | 2
33191231 | Boring centraliser dia 41 mm | each |  |  |  | 0 |  |  |  | 0 | 87 |  | 78 | 9 | 78 | 77 | 1
33191232 | Boring centraliser dia 48 mm | each |  |  |  | 0 |  |  |  | 0 | 85 |  | 83 | 2 | 83 | 82 | 1
33191234 | Bolting centraliser dia 66 mm guide | each |  |  |  | 0 |  |  |  | 0 | 163 |  | 161 | 2 | 161 | 161 | 0
7979-2630 | T38 dolly 47 mm | each | 46 | 0 | 46 | 0 | 46 |  | 43 | 3 | 43 | 5 | 47 | 1 | 47 | 43 | 4
7979-2626 | T38 dolly 39 mm | each | 7 | 0 | 7 | 0 | 7 |  | 7 | 0 | 7 | 5 | 7 | 5 | 7 | 7 | 0
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 1777 | 0 | 1750 | 27 | 1750 |  | 1750 | 0 | 1750 |  | 1690 | 60 | 1690 | 1630 | 60
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 1850 | 0 | 1847 | 3 | 1847 | 400 | 1841 | 406 | 1841 |  | 1841 | 0 | 1841 | 1700 | 141
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 2490 | 0 | 2184 | 306 | 2184 | 600 | 2690 | 94 | 2690 |  | 2664 | 26 | 2664 | 2507 | 157
See Notes sheet, note 4.

## Consumption_Issues
CONSUMPTION FROM THE STOCK USAGE ISSUE REGISTERS
Source: Stock Usage Sheets, May to August 2026. Sum of the Qty issued column by item and month.
This measures material signed out of store and recorded on a transaction. It is the second, independent measure of consumption.
Item code | Description | Unit | May (units) | June (units) | July (units) | August (units) | Total (units) |  | Note
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | 0 | 2 | 0 | 2
7580-5243A-S70 | A340 43 mm button bit | each | 110 | 0 | 10 | 120
7580-5345A-R48 | A340 45 mm button bit | each | 62 | 0 | 10 | 72
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 1 | 7 | 2 | 10
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 0 | 0 | 150 | 150
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 26 | 150 | 270 | 446
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 156 | 1350 | 728 | 2234
BMG2024S | MD bolt 2.4 m galvanised | each | 1852 | 885 | 1602 | 4339
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 0 | 0 | 0 | 0 |  | No issue transaction recorded for this item
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 20 | 0 | 780 | 800
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 3496 | 2245 | 1733 | 7474
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 200 | 230 | 369 | 799
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 6 | 23 | 32 | 61
7335-4401 | Bit adaptor T45F / T38M | each | 12 | 4 | 10 | 26
7314-6261 | Coupling sleeve T45 / T38 | each | 10 | 7 | 14 | 31
7314-3652 | Coupling sleeve T38 / T38 | each | 5 | 1 | 3 | 9
7580-5148A-S81 | A340 48 mm TC button bit | each | 0 | 0 | 10 | 10
7580-4651A-S70 | A340 51 mm retrac bit | each | 8 | 15 | 10 | 33
7580-5602P-S70 | Reaming bit A340 102 mm | each | 12 | 0 | 14 | 26
7514-1664-S70 | T38 64 mm button bit | each | 27 | 20 | 3 | 50
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 60 | 26 | 30 | 116
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 1 | 0 | 0 | 1
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 1 | 10 | 2 | 13
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 1 | 3 | 0 | 4
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 4 | 6 | 0 | 10
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 0 | 4 | 1 | 5
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 0 | 1 | 1 | 2
M2000354 | Bolting centraliser dia 70 mm front | each | 0 | 9 | 9 | 18
M2000353 | Bolting centraliser dia 70 mm back | each | 0 | 0 | 2 | 2
M33191232 | Boring centraliser dia 48 mm | each | 0 | 0 | 0 | 0 |  | No issue transaction recorded for this item
33191231 | Boring centraliser dia 41 mm | each | 4 | 3 | 5 | 12
33191232 | Boring centraliser dia 48 mm | each | 0 | 5 | 6 | 11
33191234 | Bolting centraliser dia 66 mm guide | each | 0 | 2 | 2 | 4
7979-2630 | T38 dolly 47 mm | each | 0 | 1 | 2 | 3
7979-2626 | T38 dolly 39 mm | each | 0 | 2 | 0 | 2
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 0 | 51 | 18 | 69
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 50 | 0 | 50 | 100
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 0 | 0 | 38 | 38
| Total, all items |  | 6124 | 5062 | 5916 | 17102 | 0
See Notes sheet, note 5.

## Consumption_Compare
COMPARISON OF THE TWO CONSUMPTION MEASURES
Stock count consumption against issue register consumption, by item and month.
The stock count is the costing basis. The issue register is the corroborating measure. Neither has been adjusted to match the other.
MAY 2026
Item code | Description | Unit | Stock count (units) | Issue register (units) | Gap (units) | Register capture |  | Flag
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | 7 | 0 | -7 | 0% | Check
7580-5243A-S70 | A340 43 mm button bit | each | 115 | 110 | -5 | 95.65% | Check
7580-5345A-R48 | A340 45 mm button bit | each | 72 | 62 | -10 | 86.11% | Check
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 1 | 1 | 0 | 100% | Check
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 183 | 0 | -183 | 0% | Check
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 300 | 26 | -274 | 8.667% | Check
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 743 | 156 | -587 | 21% | Check
BMG2024S | MD bolt 2.4 m galvanised | each | 2575 | 1852 | -723 | 71.92% | Check
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 0 | 0 | 0 | n/a
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 640 | 20 | -620 | 3.125% | Check
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 2740 | 3496 | 756 | 127.6% | Check
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 2291 | 200 | -2091 | 8.73% | Check
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 8 | 6 | -2 | 75% | Check
7335-4401 | Bit adaptor T45F / T38M | each | 15 | 12 | -3 | 80% | Check
7314-6261 | Coupling sleeve T45 / T38 | each | 11 | 10 | -1 | 90.91% | Check
7314-3652 | Coupling sleeve T38 / T38 | each | 5 | 5 | 0 | 100% | Check
7580-5148A-S81 | A340 48 mm TC button bit | each | 0 | 0 | 0 | n/a
7580-4651A-S70 | A340 51 mm retrac bit | each | 10 | 8 | -2 | 80% | Check
7580-5602P-S70 | Reaming bit A340 102 mm | each | 14 | 12 | -2 | 85.71% | Check
7514-1664-S70 | T38 64 mm button bit | each | 22 | 27 | 5 | 122.7% | Check
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 62 | 60 | -2 | 96.77% | Check
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 1 | 1 | 0 | 100% | Check
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 15 | 1 | -14 | 6.667% | Check
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 2 | 1 | -1 | 50% | Check
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 15 | 4 | -11 | 26.67% | Check
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 0 | 0 | 0 | n/a
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 0 | 0 | 0 | n/a
M2000354 | Bolting centraliser dia 70 mm front | each | -48 | 0 | 48 | n/a
M2000353 | Bolting centraliser dia 70 mm back | each | -34 | 0 | 34 | n/a
M33191232 | Boring centraliser dia 48 mm | each | -48 | 0 | 48 | n/a
33191231 | Boring centraliser dia 41 mm | each | 0 | 4 | 4 | n/a
33191232 | Boring centraliser dia 48 mm | each | 0 | 0 | 0 | n/a
33191234 | Bolting centraliser dia 66 mm guide | each | 0 | 0 | 0 | n/a
7979-2630 | T38 dolly 47 mm | each | 0 | 0 | 0 | n/a
7979-2626 | T38 dolly 39 mm | each | 0 | 0 | 0 | n/a
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 27 | 0 | -27 | 0% | Check
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 3 | 50 | 47 | 1667% | Check
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 306 | 0 | -306 | 0% | Check
| May 2026 total |  | 10053 | 6124 | -3929 | 60.92%
JUNE 2026
Item code | Description | Unit | Stock count (units) | Issue register (units) | Gap (units) | Register capture |  | Flag
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | 1 | 2 | 1 | 200% | Check
7580-5243A-S70 | A340 43 mm button bit | each | 0 | 0 | 0 | n/a
7580-5345A-R48 | A340 45 mm button bit | each | 0 | 0 | 0 | n/a
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 5 | 7 | 2 | 140% | Check
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 177 | 0 | -177 | 0% | Check
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 529 | 150 | -379 | 28.36% | Check
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 949 | 1350 | 401 | 142.3% | Check
BMG2024S | MD bolt 2.4 m galvanised | each | 3674 | 885 | -2789 | 24.09% | Check
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 15 | 0 | -15 | 0% | Check
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 1054 | 0 | -1054 | 0% | Check
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 2730 | 2245 | -485 | 82.23% | Check
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 408 | 230 | -178 | 56.37% | Check
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 19 | 23 | 4 | 121.1% | Check
7335-4401 | Bit adaptor T45F / T38M | each | 4 | 4 | 0 | 100% | Check
7314-6261 | Coupling sleeve T45 / T38 | each | 7 | 7 | 0 | 100% | Check
7314-3652 | Coupling sleeve T38 / T38 | each | 1 | 1 | 0 | 100% | Check
7580-5148A-S81 | A340 48 mm TC button bit | each | 0 | 0 | 0 | n/a
7580-4651A-S70 | A340 51 mm retrac bit | each | 15 | 15 | 0 | 100% | Check
7580-5602P-S70 | Reaming bit A340 102 mm | each | 2 | 0 | -2 | 0% | Check
7514-1664-S70 | T38 64 mm button bit | each | 20 | 20 | 0 | 100% | Check
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 42 | 26 | -16 | 61.9% | Check
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 0 | 0 | 0 | n/a
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 18 | 10 | -8 | 55.56% | Check
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 1 | 3 | 2 | 300% | Check
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 12 | 6 | -6 | 50% | Check
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 4 | 4 | 0 | 100% | Check
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 1 | 1 | 0 | 100% | Check
M2000354 | Bolting centraliser dia 70 mm front | each | 9 | 9 | 0 | 100% | Check
M2000353 | Bolting centraliser dia 70 mm back | each | 0 | 0 | 0 | n/a
M33191232 | Boring centraliser dia 48 mm | each | 0 | 0 | 0 | n/a
33191231 | Boring centraliser dia 41 mm | each | 0 | 3 | 3 | n/a
33191232 | Boring centraliser dia 48 mm | each | 0 | 5 | 5 | n/a
33191234 | Bolting centraliser dia 66 mm guide | each | 0 | 2 | 2 | n/a
7979-2630 | T38 dolly 47 mm | each | 3 | 1 | -2 | 33.33% | Check
7979-2626 | T38 dolly 39 mm | each | 0 | 2 | 2 | n/a
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 0 | 51 | 51 | n/a
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 406 | 0 | -406 | 0% | Check
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 94 | 0 | -94 | 0% | Check
| June 2026 total |  | 10200 | 5062 | -5138 | 49.63%
JULY 2026
Item code | Description | Unit | Stock count (units) | Issue register (units) | Gap (units) | Register capture |  | Flag
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | 1 | 0 | -1 | 0% | Check
7580-5243A-S70 | A340 43 mm button bit | each | 10 | 10 | 0 | 100% | Check
7580-5345A-R48 | A340 45 mm button bit | each | 10 | 10 | 0 | 100% | Check
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 45 | 2 | -43 | 4.444% | Check
FB39090GWA | Friction bolt 39 x 900 galvanised | each | -257 | 150 | 407 | n/a
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 401 | 270 | -131 | 67.33% | Check
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 2159 | 728 | -1431 | 33.72% | Check
BMG2024S | MD bolt 2.4 m galvanised | each | 4163 | 1602 | -2561 | 38.48% | Check
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 0 | 0 | 0 | n/a
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 2602 | 780 | -1822 | 29.98% | Check
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 4490 | 1733 | -2757 | 38.6% | Check
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 821 | 369 | -452 | 44.95% | Check
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 34 | 32 | -2 | 94.12% | Check
7335-4401 | Bit adaptor T45F / T38M | each | 16 | 10 | -6 | 62.5% | Check
7314-6261 | Coupling sleeve T45 / T38 | each | 14 | 14 | 0 | 100% | Check
7314-3652 | Coupling sleeve T38 / T38 | each | 3 | 3 | 0 | 100% | Check
7580-5148A-S81 | A340 48 mm TC button bit | each | 0 | 10 | 10 | n/a
7580-4651A-S70 | A340 51 mm retrac bit | each | 10 | 10 | 0 | 100% | Check
7580-5602P-S70 | Reaming bit A340 102 mm | each | 14 | 14 | 0 | 100% | Check
7514-1664-S70 | T38 64 mm button bit | each | 1 | 3 | 2 | 300% | Check
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 20 | 30 | 10 | 150% | Check
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 7 | 0 | -7 | 0% | Check
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 16 | 2 | -14 | 12.5% | Check
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 3 | 0 | -3 | 0% | Check
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 0 | 0 | 0 | n/a
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 1 | 1 | 0 | 100% | Check
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 1 | 1 | 0 | 100% | Check
M2000354 | Bolting centraliser dia 70 mm front | each | 12 | 9 | -3 | 75% | Check
M2000353 | Bolting centraliser dia 70 mm back | each | 2 | 2 | 0 | 100% | Check
M33191232 | Boring centraliser dia 48 mm | each | 4 | 0 | -4 | 0% | Check
33191231 | Boring centraliser dia 41 mm | each | 9 | 5 | -4 | 55.56% | Check
33191232 | Boring centraliser dia 48 mm | each | 2 | 6 | 4 | 300% | Check
33191234 | Bolting centraliser dia 66 mm guide | each | 2 | 2 | 0 | 100% | Check
7979-2630 | T38 dolly 47 mm | each | 1 | 2 | 1 | 200% | Check
7979-2626 | T38 dolly 39 mm | each | 5 | 0 | -5 | 0% | Check
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 60 | 18 | -42 | 30% | Check
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 0 | 50 | 50 | n/a
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 26 | 38 | 12 | 146.2% | Check
| July 2026 total |  | 14708 | 5916 | -8792 | 40.22%
AUGUST 2026
Item code | Description | Unit | Stock count (units) | Issue register (units) | Gap (units) | Register capture |  | Flag
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | -1 | 2 | 3 | n/a
7580-5243A-S70 | A340 43 mm button bit | each | 0 | 120 | 120 | n/a
7580-5345A-R48 | A340 45 mm button bit | each | 25 | 72 | 47 | 288% | Check
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 1 | 10 | 9 | 1000% | Check
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 80 | 150 | 70 | 187.5% | Check
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 320 | 446 | 126 | 139.4% | Check
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 2286 | 2234 | -52 | 97.73% | Check
BMG2024S | MD bolt 2.4 m galvanised | each | 3319 | 4339 | 1020 | 130.7% | Check
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | 209 | 0 | -209 | 0% | Check
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | 3230 | 800 | -2430 | 24.77% | Check
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | 4398 | 7474 | 3076 | 169.9% | Check
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 769 | 799 | 30 | 103.9% | Check
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 24 | 61 | 37 | 254.2% | Check
7335-4401 | Bit adaptor T45F / T38M | each | 16 | 26 | 10 | 162.5% | Check
7314-6261 | Coupling sleeve T45 / T38 | each | 20 | 31 | 11 | 155% | Check
7314-3652 | Coupling sleeve T38 / T38 | each | 0 | 9 | 9 | n/a
7580-5148A-S81 | A340 48 mm TC button bit | each | 35 | 10 | -25 | 28.57% | Check
7580-4651A-S70 | A340 51 mm retrac bit | each | 15 | 33 | 18 | 220% | Check
7580-5602P-S70 | Reaming bit A340 102 mm | each | 12 | 26 | 14 | 216.7% | Check
7514-1664-S70 | T38 64 mm button bit | each | 12 | 50 | 38 | 416.7% | Check
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 70 | 116 | 46 | 165.7% | Check
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 19 | 1 | -18 | 5.263% | Check
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 24 | 13 | -11 | 54.17% | Check
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 4 | 4 | 0 | 100% | Check
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 4 | 10 | 6 | 250% | Check
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 1 | 5 | 4 | 500% | Check
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 1 | 2 | 1 | 200% | Check
M2000354 | Bolting centraliser dia 70 mm front | each | 4 | 18 | 14 | 450% | Check
M2000353 | Bolting centraliser dia 70 mm back | each | 1 | 2 | 1 | 200% | Check
M33191232 | Boring centraliser dia 48 mm | each | 2 | 0 | -2 | 0% | Check
33191231 | Boring centraliser dia 41 mm | each | 1 | 12 | 11 | 1200% | Check
33191232 | Boring centraliser dia 48 mm | each | 1 | 11 | 10 | 1100% | Check
33191234 | Bolting centraliser dia 66 mm guide | each | 0 | 4 | 4 | n/a
7979-2630 | T38 dolly 47 mm | each | 4 | 3 | -1 | 75% | Check
7979-2626 | T38 dolly 39 mm | each | 0 | 2 | 2 | n/a
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 60 | 69 | 9 | 115% | Check
BLW15003RWA | Barrel and 3 piece wedge anchor | each | 141 | 100 | -41 | 70.92% | Check
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | 157 | 38 | -119 | 24.2% | Check
| August 2026 total |  | 15264 | 17102 | 1838 | 112%
OVERALL
Measure |  |  | Stock count (units) | Issue register (units) | Gap (units) | Register capture
All items, period total |  |  | 34961 | 17102 | -17859 | 48.92%
See Notes sheet, note 6.
See Notes sheet, note 7.

## A_Scaling
SHEET A SCALING
Scaling and sounding of the face and walls before development drilling.
Quantities are measured consumption. Cost = quantity x unit cost. All costs in United States dollars.
Item code | Description | Unit | Unit cost (US$) | May (units) | June (units) | July (units) | August (units) | Total (units) | Units per metre | Total cost (US$), period | Cost per metre (US$/m), period
Drilling consumables
7324-8043-20 | Drifter rod T38 H35 A340 L=430, scaling rod | each | x | 7 | 1 | 1 | 0 | 9 | 0.0065416 | x | x
7580-5243A-S70 | A340 43 mm button bit | each | - | 115 | 0 | 10 | 0 | 125 | 0.090855 | - | -
7580-5345A-R48 | A340 45 mm button bit | each | - | 72 | 0 | 10 | 25 | 107 | 0.077772 | - | -
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | - | 1 | 5 | 45 | 1 | 52 | 0.037796 | - | -
| Drilling consumables, subtotal | [6 empty] | 293 | 0.21296 | x | x
| SHEET TOTAL | [8 empty] | x | x
Key
| x | No unit price in the source data.
| - | Same item as the face drill uses. Counted once, on sheet C.

## B_Ground_Support
SHEET B GROUND SUPPORT, BOLTING AND MESHING
Installation of primary ground support: bolts, bearing plates and mesh.
Quantities are measured consumption. Cost = quantity x unit cost. All costs in United States dollars.
Item code | Description | Unit | Unit cost (US$) | May (units) | June (units) | July (units) | August (units) | Total (units) | Units per metre | Total cost (US$), period | Cost per metre (US$/m), period
Bolts
FB39090GWA | Friction bolt 39 x 900 galvanised | each | 7.3845 | 183 | 177 | 0 | 80 | 440 | 0.31981 | 3249.1776 | 2.3616
FB47090GWA | Friction bolt 47 x 900 galvanised | each | 12.8972 | 300 | 529 | 401 | 320 | 1550 | 1.1266 | 19990.6987 | 14.53
FB47-2400G | Friction bolt 47 x 2400 galvanised | each | 15.9311 | 743 | 949 | 2159 | 2286 | 6137 | 4.4606 | 97769.3141 | 71.0627
BMG2024S | MD bolt 2.4 m galvanised | each | 65.8783 | 2575 | 3674 | 4163 | 3319 | 13731 | 9.9802 | 904575.3161 | 657.4818
| Bolts, subtotal | [6 empty] | 21858 | 15.8873 | 1025584.5065 | 745.4362
Bearing plates
D1515441GWA | Plate dome 150 x 150 x 4, 41H galvanised | each | - | 0 | 15 | 0 | 209 | 224 | 0.16281 | - | -
CBP328154-47G | D/Fly plate 300 x 280 galvanised | each | - | 640 | 1054 | 2602 | 3230 | 7526 | 5.4702 | - | -
BPG3002806 | Combi plate 300 x 280 x 6 mm galvanised | each | - | 2740 | 2730 | 4490 | 4398 | 14358 | 10.436 | - | -
| Bearing plates, subtotal | [6 empty] | 22108 | 16.069 | x | x
Mesh
MESH2.4X4.5 | Mesh 2.40 x 4.50 m galvanised | sheet | 82.4854 | 2291 | 408 | 821 | 769 | 4289 | 3.1174 | 353779.9267 | 257.1415
| Mesh, subtotal | [6 empty] | 4289 | 3.1174 | 353779.9267 | 257.1415
| SHEET TOTAL | [8 empty] | 1379364.4332 | 1002.5777
Key
| - | Plate cost is inside the bolt price, quoted Bolt and Plate.

## C_Face_Drilling
SHEET C DEVELOPMENT DRILLING, FACE DRILL
Face drilling for blast rounds. This sheet carries all shared drill steel.
Quantities are measured consumption. Cost = quantity x unit cost. All costs in United States dollars.
Item code | Description | Unit | Unit cost (US$) | May (units) | June (units) | July (units) | August (units) | Total (units) | Units per metre | Total cost (US$), period | Cost per metre (US$/m), period
Shanks
7304-7669-01 | Shank T38 RD520/525 D45 L525 | each | 308.1 | 1 | 5 | 45 | 1 | 52 | 0.037796 | 16021.2 | 11.6449
7305-7669-01 | Shank T45 RD520/525 D45 L525 | each | 5568.55 | 8 | 19 | 34 | 24 | 85 | 0.061781 | 473326.75 | 344.033
| Shanks, subtotal | [6 empty] | 137 | 0.099577 | 489347.95 | 355.6778
Couplings and adaptors
7335-4401 | Bit adaptor T45F / T38M | each | 4453.45 | 15 | 4 | 16 | 16 | 51 | 0.037069 | 227125.95 | 165.0843
7314-6261 | Coupling sleeve T45 / T38 | each | 1925.47 | 11 | 7 | 14 | 20 | 52 | 0.037796 | 100124.44 | 72.7745
7314-3652 | Coupling sleeve T38 / T38 | each | 69.96 | 5 | 1 | 3 | 0 | 9 | 0.0065416 | 629.64 | 0.45765
| Couplings and adaptors, subtotal | [6 empty] | 112 | 0.081406 | 327880.03 | 238.3164
Bits
7580-5243A-S70 | A340 43 mm button bit | each | 66.52 | 115 | 0 | 10 | 0 | 125 | 0.090855 | 8315 | 6.0437
7580-5345A-R48 | A340 45 mm button bit | each | 78.93 | 72 | 0 | 10 | 25 | 107 | 0.077772 | 8445.51 | 6.1385
7580-5148A-S81 | A340 48 mm TC button bit | each | 108.19 | 0 | 0 | 0 | 35 | 35 | 0.025439 | 3786.65 | 2.7523
7580-4651A-S70 | A340 51 mm retrac bit | each | 94.13 | 10 | 15 | 10 | 15 | 50 | 0.036342 | 4706.5 | 3.4209
7580-5602P-S70 | Reaming bit A340 102 mm | each | 343.33 | 14 | 2 | 14 | 12 | 42 | 0.030527 | 14419.86 | 10.4809
7514-1664-S70 | T38 64 mm button bit | each | 136.44 | 22 | 20 | 1 | 12 | 55 | 0.039976 | 7504.2 | 5.4544
7580-6045-F49 | Speedy bit A340 45 mm XT49 | each | 79.73 | 62 | 42 | 20 | 70 | 194 | 0.14101 | 15467.62 | 11.2425
| Bits, subtotal | [6 empty] | 608 | 0.44192 | 62645.34 | 45.5332
Rods
7324-8037-20 | Drifter rod T38 H35 A340 L=370, drilling steel | each | 498.85 | 1 | 0 | 7 | 19 | 27 | 0.019625 | 13468.95 | 9.7898
7324-7949-20 | Drifter rod T38 R39 A340 L=491, speed rod | each | 639 | 15 | 18 | 16 | 24 | 73 | 0.053059 | 46647 | 33.9049
7324-4731-85 | MF rod T38 R39 L=3050 mm | each | 439.59 | 2 | 1 | 3 | 4 | 10 | 0.0072684 | 4395.9 | 3.1951
7324-4331C-30 | T38 extension round rod L=3050 mm | each | 317.43 | 15 | 12 | 0 | 4 | 31 | 0.022532 | 9840.33 | 7.1523
7324-4309C-30 | Extension rod T38 R39 L=915 mm | each | 184.75 | 0 | 4 | 1 | 1 | 6 | 0.004361 | 1108.5 | 0.8057
7324-4709C-20 | MF rod T38 R39 L=915 mm | each | 276.63 | 0 | 1 | 1 | 1 | 3 | 0.0021805 | 829.89 | 0.6032
| Rods, subtotal | [6 empty] | 150 | 0.10903 | 76290.57 | 55.4511
Centralisers and dollies
M2000354 | Bolting centraliser dia 70 mm front | each | 45.12 | 0 | 9 | 12 | 4 | 25 | 0.018171 | 1128 | 0.81988
M2000353 | Bolting centraliser dia 70 mm back | each | 68 | 0 | 0 | 2 | 1 | 3 | 0.0021805 | 204 | 0.14828
M33191232 | Boring centraliser dia 48 mm | each | 61.09 | 0 | 0 | 4 | 2 | 6 | 0.004361 | 366.54 | 0.26642
33191231 | Boring centraliser dia 41 mm | each | 1884.83 | 0 | 0 | 9 | 1 | 10 | 0.0072684 | 18848.3 | 13.6997
33191232 | Boring centraliser dia 48 mm | each | 1733.67 | 0 | 0 | 2 | 1 | 3 | 0.0021805 | 5201.01 | 3.7803
33191234 | Bolting centraliser dia 66 mm guide | each | 1376.29 | 0 | 0 | 2 | 0 | 2 | 0.0014537 | 2752.58 | 2.0007
7979-2630 | T38 dolly 47 mm | each | 96.3 | 0 | 3 | 1 | 4 | 8 | 0.0058147 | 770.4 | 0.55996
7979-2626 | T38 dolly 39 mm | each | 96.3 | 0 | 0 | 5 | 0 | 5 | 0.0036342 | 481.5 | 0.34997
| Centralisers and dollies, subtotal | [6 empty] | 62 | 0.045064 | 29752.33 | 21.6252
| SHEET TOTAL | [8 empty] | 985916.22 | 716.6037
Key
| x | No unit price in the source data. Enter prices here and the model completes.
| Units per metre | Measured consumption. A complete result that needs no price.

## D_Cable_Bolting
SHEET D CABLE BOLTING
Cable bolt installation in crosscuts, wide spans, poor ground and stock brows.
Quantities are measured consumption. Cost = quantity x unit cost. All costs in United States dollars.
Item code | Description | Unit | Unit cost (US$) | May (units) | June (units) | July (units) | August (units) | Total (units) | Units per metre | Total cost (US$), period | Cost per metre (US$/m), period
Cable bolts and hardware
CBD1B065DC05WA | Cable bolt twin strand bulbed 15.2 mm | each | 68.072 | 27 | 0 | 60 | 60 | 147 | 0.10685 | 10006.5782 | 7.2732
BLW15003RWA | Barrel and 3 piece wedge anchor | each | x | 3 | 406 | 0 | 141 | 550 | 0.39976 | x | x
FCB20203H222WA | Plate flat 200 x 200 x 12 mm | each | - | 306 | 94 | 26 | 157 | 583 | 0.42375 | - | -
| Cable bolts and hardware, subtotal | [6 empty] | 1280 | 0.93036 | 10006.5782 | 7.2732
| SHEET TOTAL | [8 empty] | 10006.5782 | 7.2732
Key
| x | No unit price in the source data.
| - | Plate cost is inside the bolt price.

## DRM
DRILLED METRES
DRM = total metres of hole drilled. Drill steel wears with metres of hole drilled, not metres of heading advanced.
Bolt hole metres come from bolts installed. Face metres come from the holes actually drilled, recorded in LiveMine.
1 BOLT HOLE DRILLED METRES, CALCULATED FROM BOLTS INSTALLED
Bolt type | Hole length (m) | May (drilled m) | June (drilled m) | July (drilled m) | August (drilled m) | Total (drilled m) |  | Bolts installed, period | Calculation
MD bolt 2.4 m galvanised | 2.4 | 6180 | 8817.6 | 9991.2 | 7965.6 | 32954.4 |  | 13731 | 13,731 bolts x 2.4 m = 32,954 drilled m
Friction bolt 47 x 2400 galvanised | 2.4 | 1783.2 | 2277.6 | 5181.6 | 5486.4 | 14728.8 |  | 6137 | 6,137 bolts x 2.4 m = 14,729 drilled m
Friction bolt 47 x 900 galvanised | 0.9 | 270 | 476.1 | 360.9 | 288 | 1395 |  | 1550 | 1,550 bolts x 0.9 m = 1,395 drilled m
Friction bolt 39 x 900 galvanised | 0.9 | 164.7 | 159.3 | 0 | 72 | 396 |  | 440 | 440 bolts x 0.9 m = 396 drilled m
Cable bolt twin strand bulbed 15.2 mm | 6.5 | 175.5 | 0 | 390 | 390 | 955.5 |  | 147 | 147 bolts x 6.5 m = 956 drilled m
Total bolt hole drilled metres |  | 8573.4 | 11730.6 | 15923.7 | 14202 | 50429.7
2 FACE DRILLED METRES, FROM THE LIVEMINE JUMBO PLOD
Term | Unit | May | June | July | August | Period total |  | Source
Face holes drilled | holes | 4459 | 4777 | 7198 | 5983 | 22417 |  | LiveMine Jumbo PLOD, Face Hole Drilled
Reaming holes drilled | holes | 380 | 371 | 575 | 549 | 1875 |  | LiveMine Jumbo PLOD, Ream Hole Drilled
Drilled length per hole | m | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 |  | LiveMine Jumbo PLOD, Hole Length
Face drilled metres | drilled m | 20807.7 | 22136.4 | 33423.9 | 28087.6 | 104455.6 |  | ( face holes + reaming holes ) x drilled length per hole
Metres advanced | m | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818
Face drilled metres per advance metre | drilled m / m | 76.9413 | 69.9154 | 84.0223 | 71.8414 | 75.9225
3 TOTAL DRILLED METRES
Term | Unit | May | June | July | August | Period total |  | Note
DRM, total drilled metres | drilled m | 29381.1 | 33867 | 49347.6 | 42289.6 | 154885.3
DRM per advance metre | drilled m / m | 108.6434 | 106.9652 | 124.0519 | 108.1667 | 112.5769
4 BIT LIFE, THE TWO BITS UNDER INVESTIGATION
See Notes sheet, note 8.
Bit |  | Bits consumed, period | Drilled metres per bit, from records | Resharpens per bit, from the trial | Drilled metres per bit, from the trial |  | Note
A340 43 mm button bit |  | 125 | 224.7008 | [5 empty] | Enter the trial result in the two shaded cells
A340 48 mm TC button bit |  | 35 | 802.5029 | [5 empty] | Enter the trial result in the two shaded cells
Difference, 48 mm against 43 mm |  |  | 577.8021
See Notes sheet, note 9.

## Plan_vs_Actual
PLAN VERSUS ACTUAL GROUND SUPPORT, BY GROUND CLASS
V = actual per metre - design per metre. V % = ( actual - design ) / design x 100
Design quantities are read from the GSS drawings and are per cut. They are converted to a per metre basis using the cut length on the Inputs sheet.
1 METRES DRIVEN IN EACH GROUND CLASS
Ground class | Ground condition | May (m) | June (m) | July (m) | August (m) | Period (m) |  | Share of total
GSS_01 | Good ground, Q >= 10 | 191.654 | 140.782 | 138.592 | 152.678 | 623.706 |  | 45.33%
GSS_02 | Fair to poor ground, 10 > Q >= 4 | 78.782 | 175.835 | 41.815 | 238.289 | 534.721 |  | 38.87%
GSS_03 | Poor ground, Q < 4 | 0 | 0 | 217.391 | 0 | 217.391 |  | 15.8%
Total |  | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818
2 DESIGN QUANTITY PER METRE, WEIGHTED BY GROUND CLASS
Consumable | Design per cut | May (per m) | June (per m) | July (per m) | August (per m) | Period (per m) |  | Note
MD bolt 2.4 m x 47 mm | see Inputs section 6 | 6.9391 | 5.7509 | 5.3178 | 5.5073 | 5.79 |  | Weighted by the metres driven in each ground class
Split set 2.4 m x 47 mm | see Inputs section 6 | 1.3109 | 2.4991 | 2.9322 | 2.7427 | 2.46 |  | Weighted by the metres driven in each ground class
Stubby split set 0.9 m x 39 mm | see Inputs section 6 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  | Weighted by the metres driven in each ground class
Mesh sheet 4.5 x 2.4 m | see Inputs section 6 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | Weighted by the metres driven in each ground class
3 ACTUAL QUANTITY PER METRE
Consumable |  | May (per m) | June (per m) | July (per m) | August (per m) | Period (per m) |  | Units consumed, period
MD bolt 2.4 m x 47 mm |  | 9.5217 | 11.6039 | 10.4651 | 8.4892 | 9.9802 |  | 13731
Split set 2.4 m x 47 mm |  | 2.7474 | 2.9973 | 5.4274 | 5.847 | 4.4606 |  | 6137
Stubby split set 0.9 m x 39 mm |  | 0.67669 | 0.55904 | 0 | 0.20462 | 0.31981 |  | 440
Mesh sheet 4.5 x 2.4 m |  | 8.4715 | 1.2886 | 2.0639 | 1.9669 | 3.1174 |  | 4289
4 VARIANCE AGAINST DESIGN
Consumable | Unit | May | June | July | August | Period total |  | Meaning
MD bolt 2.4 m x 47 mm variance | units / m | 2.5826 | 5.853 | 5.1473 | 2.9819 | 4.1902 |  | Positive means more consumed than the design requires
MD bolt 2.4 m x 47 mm variance, per cent | % | 37.22% | 101.8% | 96.79% | 54.14% | 72.37%
Split set 2.4 m x 47 mm variance | units / m | 1.4365 | 0.49821 | 2.4952 | 3.1044 | 2.0006 |  | Positive means more consumed than the design requires
Split set 2.4 m x 47 mm variance, per cent | % | 109.6% | 19.94% | 85.1% | 113.2% | 81.33%
Stubby split set 0.9 m x 39 mm variance | units / m | -2.0733 | -2.191 | -2.75 | -2.5454 | -2.4302 |  | Positive means more consumed than the design requires
Stubby split set 0.9 m x 39 mm variance, per cent | % | -75.39% | -79.67% | -100% | -92.56% | -88.37%
Mesh sheet 4.5 x 2.4 m variance | units / m | 6.9715 | -0.21138 | 0.56386 | 0.46692 | 1.6174 |  | Positive means more consumed than the design requires
Mesh sheet 4.5 x 2.4 m variance, per cent | % | 464.8% | -14.09% | 37.59% | 31.13% | 107.8%
5 CLASSIFICATION OF ANY OVER CONSUMPTION
Month | Consumable | Variance (units/m) | Classification | Evidence relied on |  |  | Action
May 2026 | MD bolt 2.4 m x 47 mm | 2.5826
May 2026 | Split set 2.4 m x 47 mm | 1.4365
May 2026 | Stubby split set 0.9 m x 39 mm | -2.0733
May 2026 | Mesh sheet 4.5 x 2.4 m | 6.9715
June 2026 | MD bolt 2.4 m x 47 mm | 5.853
June 2026 | Split set 2.4 m x 47 mm | 0.49821
June 2026 | Stubby split set 0.9 m x 39 mm | -2.191
June 2026 | Mesh sheet 4.5 x 2.4 m | -0.21138
July 2026 | MD bolt 2.4 m x 47 mm | 5.1473
July 2026 | Split set 2.4 m x 47 mm | 2.4952
July 2026 | Stubby split set 0.9 m x 39 mm | -2.75
July 2026 | Mesh sheet 4.5 x 2.4 m | 0.56386
August 2026 | MD bolt 2.4 m x 47 mm | 2.9819
August 2026 | Split set 2.4 m x 47 mm | 3.1044
August 2026 | Stubby split set 0.9 m x 39 mm | -2.5454
August 2026 | Mesh sheet 4.5 x 2.4 m | 0.46692
See Notes sheet, note 10.
6 DESIGN PER METRE AT A RANGE OF CUT LENGTHS, PERIOD BASIS
Cut length (m) |  | MD bolt design (per m) | MD bolt actual (per m) | Variance (per m) | Variance (per cent) |  |  | Mesh design (per m)
3 |  | 7.3431 | 8.4892 | 1.1461 |  | 15.61% |  | 3.6667
3.2 |  | 6.8841 | 8.4892 | 1.6051 |  | 23.32% |  | 3.4375
3.4 |  | 6.4792 | 8.4892 | 2.01 |  | 31.02% |  | 3.2353
3.6 |  | 6.1192 | 8.4892 | 2.37 |  | 38.73% |  | 3.0556
3.8 |  | 5.7972 | 8.4892 | 2.692 |  | 46.44% |  | 2.8947
4 |  | 5.5073 | 8.4892 | 2.9819 |  | 54.14% |  | 2.75
See Notes sheet, note 11.
See Notes sheet, note 12.

## Unit_Cost
DEVELOPMENT UNIT COST
Equations 1 to 4, cost per drilled metre, and the advance rate scenarios.
All costs in United States dollars. Metres are survey measured. Whole underground mine.
1 EQUATION 2 UC support = ( C bolts + C mesh + C plates + C resin + C cable ) ÷ m
Term | Unit | May 2026 | June 2026 | July 2026 | August 2026 | Period total |  | Note
C bolts | US$ | 186694.0494 | 265285.3007 | 313818.5638 | 259786.5926 | 1025584.5065 |  | Price includes the plate
C mesh | US$ | 188974.076 | 33654.0476 | 67720.5222 | 63431.2809 | 353779.9267 |  | 10.8 m2 per sheet
C plates | US$ | 0 | 0 | 0 | 0 | 0 |  | Zero, sits inside the bolt price
C resin and grout | US$ | 0 | 0 | 0 | 0 | 0 |  | Zero, no unit price available
C cable bolts | US$ | 1837.9429 | 0 | 4084.3176 | 4084.3176 | 10006.5782 |  | Reported separately
Total ground support consumable cost | US$ | 377506.0684 | 298939.3483 | 385623.4037 | 327302.1911 | 1389371.0114
m, metres advanced | m | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818
UC support | US$ / m | 1395.9165 | 944.1671 | 969.395 | 837.1607 | 1009.8509
2 EQUATION 1 UC drill = ( C bits + C rods + C shanks + C couplings + C centralisers ) ÷ m
Term | Unit | May 2026 | June 2026 | July 2026 | August 2026 | Period total |  | Note
C bits | US$ | 27025.62 | 8176.07 | 8933.46 | 18510.19 | 62645.34 |  | Quantity x unit price, from C_Face_Drilling
C rods | US$ | 15724.48 | 16766.38 | 15496.1 | 28303.61 | 76290.57 |  | Quantity x unit price, from C_Face_Drilling
C shanks | US$ | 44856.5 | 107342.95 | 203195.2 | 133953.3 | 489347.95 |  | Quantity x unit price, from C_Face_Drilling
C couplings | US$ | 88331.72 | 31362.05 | 98421.66 | 109764.6 | 327880.03 |  | Quantity x unit price, from C_Face_Drilling
C centralisers and dollies | US$ | 0 | 694.98 | 24682.99 | 4374.36 | 29752.33 |  | Quantity x unit price, from C_Face_Drilling
Total drilling consumable cost | US$ | 175938.32 | 164342.43 | 350729.41 | 294906.06 | 985916.22
m, metres advanced | m | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818
UC drill, per metre advanced | US$ / m | 650.5729 | 519.0575 | 881.6772 | 754.2991 | 716.6037
DRM, total drilled metres | drilled m | 29381.1 | 33867 | 49347.6 | 42289.6 | 154885.3
UC drill per drilled metre | US$ / drilled m | 5.9881 | 4.8526 | 7.1073 | 6.9735 | 6.3655
See Notes sheet, note 13.
See Notes sheet, note 14.
3 EQUATION 3 UC total = UC drill + UC support
Term | Unit | May 2026 | June 2026 | July 2026 | August 2026 | Period total |  | Note
UC support, from Equation 2 | US$ / m | 1395.9165 | 944.1671 | 969.395 | 837.1607 | 1009.8509
UC drill, from Equation 1 | US$ / m | 650.5729 | 519.0575 | 881.6772 | 754.2991 | 716.6037
Consumable unit cost, UC drill + UC support | US$ / m | 2046.4893 | 1463.2246 | 1851.0722 | 1591.4598 | 1726.4545
UC total | US$ / m | 2046.4893 | 1463.2246 | 1851.0722 | 1591.4598 | 1726.4545
4 ADVANCE RATE AGAINST CONSUMABLE UNIT COST
Scenario, on the August basis | Metres advanced | If consumption stays at the same total (US$/m) |  | If consumption stays at the same rate per metre (US$/m) |  |  |  | Change in the first case
Advance as achieved in July | 390.967 | 1591.4598 |  | 1591.4598 |  |  |  | 0%
Advance 15 per cent higher | 449.612 | 1383.8781 |  | 1591.4598 |  |  |  | -13.04%
Advance 30 per cent higher | 508.2571 | 1224.1998 |  | 1591.4598 |  |  |  | -23.08%
See Notes sheet, note 15.
5 EQUATION 4 WHY THE CONSUMABLE UNIT COST MOVED
Term | Unit | May to June | June to July | July to August |  |  | Meaning
U0, unit cost in the earlier month | US$ / m | 2046.4893 | 1463.2246 | 1851.0722
U1, unit cost in the later month | US$ / m | 1463.2246 | 1851.0722 | 1591.4598
C0, total consumable cost in the earlier month | US$ | 553444.3884 | 463281.7783 | 736352.8137
C1, total consumable cost in the later month | US$ | 463281.7783 | 736352.8137 | 622208.2511
A0, metres advanced in the earlier month | m | 270.436 | 316.617 | 397.798
A1, metres advanced in the later month | m | 316.617 | 397.798 | 390.967
Total change in unit cost | US$ / m | -583.2647 | 387.8476 | -259.6124
Change caused by consumption | US$ / m | -333.3972 | 862.4649 | -286.941 |  |  |  | More or less material used
Change caused by advance rate | US$ / m | -249.8675 | -474.6173 | 27.3286 |  |  |  | Spend spread over more or fewer metres
Check, the two causes sum to the total | US$ / m | 0 | 0 | 0 |  |  |  | Reads 0.000000, exact

## Portal_Analysis
ANALYSIS BY HEADING AND BY PORTAL
May, June, July and August 2026. Every heading in all four months is confirmed to a portal.
The Northern Portal is driven entirely in GSS_02 and GSS_03 ground. The Southern Portal is driven entirely in GSS_01 ground.
1 DEVELOPMENT ADVANCE BY HEADING
Heading | Portal | May 2026 (m) | June 2026 (m) | July 2026 (m) | August 2026 (m) | Total (m) | Share of portal | Share of mine | Ground support standard
North Decline | Northern | 55.882 | 81.29 | 108.092 | 95.452 | 340.716 | 45.05% | 24.76% | GSS_02, GSS_03
North Shoot Decline (NS_1040_ACC_N) | Northern | 0 | 71.538 | 100.974 | 31.787 | 204.299 | 27.01% | 14.85% | GSS_02, GSS_03
NS_1020_ACC_W | Northern | 0 | 0 | 0 | 57.558 | 57.558 | 7.61% | 4.184% | GSS_02
NS_1020_RAD_N | Northern | 0 | 0 | 0 | 32.709 | 32.709 | 4.324% | 2.377% | GSS_02
N_1040_ACCESS (NS 1040 access) | Northern | 27.178 | 0 | 0 | 0 | 27.178 | 3.593% | 1.975% | GSS_01, GSS_02
NS_1040_DSP02_W | Northern | 0 | 0 | 25.788 | 0 | 25.788 | 3.409% | 1.874% | GSS_02
NS_1040_LSP01_W | Northern | 0 | 0 | 24.352 | 0 | 24.352 | 3.22% | 1.77% | GSS_03
NS_1040_SP_E | Northern | 0 | 23.007 | 0 | 0 | 23.007 | 3.042% | 1.672% | GSS_02
NS_1020_DSMP | Northern | 0 | 0 | 0 | 10.505 | 10.505 | 1.389% | 0.7635% | GSS_02
NS_1020_LSP01 | Northern | 0 | 0 | 0 | 10.278 | 10.278 | 1.359% | 0.747% | GSS_02
South Decline | Southern | 75.154 | 70.356 | 95.817 | 66.894 | 308.221 | 49.76% | 22.4% | GSS_01
MS900_DDR_N | Southern | 65.685 | 0 | 0 | 0 | 65.685 | 10.6% | 4.774% | GSS_01
MS_0900_RAD_E | Southern | 0 | 39.551 | 17.112 | 0 | 56.663 | 9.148% | 4.118% | GSS_01
MS_900_RAD_E | Southern | 0 | 0 | 0 | 32.861 | 32.861 | 5.305% | 2.388% | GSS_01
MS_DSP06 | Southern | 0 | 0 | 0 | 24.425 | 24.425 | 3.943% | 1.775% | GSS_01
S890_SP_W | Southern | 24.029 | 0 | 0 | 0 | 24.029 | 3.879% | 1.747% | GSS_01
MS_0870_DSP05_W | Southern | 0 | 0 | 23.463 | 0 | 23.463 | 3.788% | 1.705% | GSS_01
MS_0900_SP_S | Southern | 0 | 19.667 | 0 | 0 | 19.667 | 3.175% | 1.429% | GSS_01
MS900_ACC_E | Southern | 17.508 | 0 | 0 | 0 | 17.508 | 2.826% | 1.273% | GSS_01
MS_PMP_STN1 | Southern | 0 | 0 | 0 | 16.689 | 16.689 | 2.694% | 1.213% | GSS_01
MS_0875_SMP_W | Southern | 0 | 11.208 | 0 | 0 | 11.208 | 1.809% | 0.8146% | GSS_01
MS_900_RAD_N | Southern | 0 | 0 | 0 | 6.07 | 6.07 | 0.9799% | 0.4412% | GSS_01
MS_840_DSMP W | Southern | 0 | 0 | 0 | 5.739 | 5.739 | 0.9265% | 0.4171% | GSS_01
S900_SMP_W | Southern | 5 | 0 | 0 | 0 | 5 | 0.8072% | 0.3634% | GSS_01
MS_0900_SP_E | Southern | 0 | 0 | 2.2 | 0 | 2.2 | 0.3552% | 0.1599% | GSS_01
Total, both portals |  | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818
2 PORTAL AND WHOLE MINE RESULTS
Measure | Unit | Northern Portal | Southern Portal | Whole mine |  |  |  | Note
Metres advanced, May 2026 | m | 83.06 | 187.376 | 270.436
Metres advanced, June 2026 | m | 175.835 | 140.782 | 316.617
Metres advanced, July 2026 | m | 259.206 | 138.592 | 397.798
Metres advanced, August 2026 | m | 238.289 | 152.678 | 390.967
Metres advanced, May to August | m | 756.39 | 619.428 | 1375.818 |  |  |  |  | Measured by survey
Ground support consumable cost, May 2026 | US$ | 149771.4293 | 227734.6391 | 377506.0684 |  |  |  |  | Split, see Inputs
Ground support consumable cost, June 2026 | US$ | 179716.5911 | 119222.7572 | 298939.3483 |  |  |  |  | Split, see Inputs
Ground support consumable cost, July 2026 | US$ | 255241.019 | 130382.3847 | 385623.4037 |  |  |  |  | Split, see Inputs
Ground support consumable cost, August 2026 | US$ | 199486.1761 | 127816.015 | 327302.1911 |  |  |  |  | Split, see Inputs
Ground support consumable cost, May to August | US$ | 784215.2155 | 605155.7959 | 1389371.0114
UC support, May 2026 | US$ / m | 1803.1716 | 1215.3885 | 1395.9165
UC support, June 2026 | US$ / m | 1022.0752 | 846.8608 | 944.1671
UC support, July 2026 | US$ / m | 984.7034 | 940.7641 | 969.395
UC support, August 2026 | US$ / m | 837.1607 | 837.1607 | 837.1607
UC support, May to August | US$ / m | 1036.7869 | 976.9591 | 1009.8509
Drilling consumable cost, May 2026 | US$ | 71007.9642 | 104930.3558 | 175938.32 |  |  |  |  | Split by measured drilled metres
Drilling consumable cost, June 2026 | US$ | 92546.3684 | 71796.0616 | 164342.43 |  |  |  |  | Split by measured drilled metres
Drilling consumable cost, July 2026 | US$ | 227175.9434 | 123553.4666 | 350729.41 |  |  |  |  | Split by measured drilled metres
Drilling consumable cost, August 2026 | US$ | 189614.9466 | 105291.1134 | 294906.06 |  |  |  |  | Split by measured drilled metres
Drilling consumable cost, May to August | US$ | 580345.2226 | 405570.9974 | 985916.22
UC drill, May to August | US$ / m | 767.2566 | 654.7508 | 716.6037
UC total consumable, May to August | US$ / m | 1804.0435 | 1631.7099 | 1726.4545 |  |  |  |  | Support plus drilling
3 RECONCILIATION CHECKS
Check | Unit | Value | Result
Sum of headings less both portals combined |  | 0 | Reconciles
Northern plus Southern metres less combined |  | 0 | Reconciles
Northern plus Southern cost less combined |  | 0 | Reconciles
May to August mine cost less Equation 2 total |  | 0 | Reconciles

## Pareto
PARETO ANALYSIS OF CONSUMABLE COST
P i = C i ÷ Σ C i × 100 Cum i = Σ ( C 1 … C i ) ÷ Σ C i × 100
All priced consumables, ground support and drilling, over the whole four month period May to August 2026, not a single month.
Rank and consumable | Activity | Total cost (US$) | Cost per metre (US$/m) | Share of total | Cumulative share | In the top 80 per cent | Note
1. MD bolt 2.4 m galvanised | Ground support | 904575.3161 | 657.4818 | 38.08% | 38.08% | Yes
2. Shank T45 RD520/525 D45 L525 | Face drilling | 473326.75 | 344.033 | 19.93% | 58.01% | Yes
3. Mesh 2.40 x 4.50 m galvanised | Ground support | 353779.9267 | 257.1415 | 14.89% | 72.9% | Yes
4. Bit adaptor T45F / T38M | Face drilling | 227125.95 | 165.0843 | 9.562% | 82.47% | Yes
5. Coupling sleeve T45 / T38 | Face drilling | 100124.44 | 72.7745 | 4.215% | 86.68% | No
6. Friction bolt 47 x 2400 galvanised | Ground support | 97769.3141 | 71.0627 | 4.116% | 90.8% | No
7. Drifter rod T38 R39 A340 L=491, speed rod | Face drilling | 46647 | 33.9049 | 1.964% | 92.76% | No
8. Friction bolt 47 x 900 galvanised | Ground support | 19990.6987 | 14.53 | 0.8416% | 93.6% | No
9. Boring centraliser dia 41 mm | Face drilling | 18848.3 | 13.6997 | 0.7935% | 94.4% | No
10. Shank T38 RD520/525 D45 L525 | Face drilling | 16021.2 | 11.6449 | 0.6745% | 95.07% | No
11. Speedy bit A340 45 mm XT49 | Face drilling | 15467.62 | 11.2425 | 0.6512% | 95.72% | No
12. Reaming bit A340 102 mm | Face drilling | 14419.86 | 10.4809 | 0.6071% | 96.33% | No
13. Drifter rod T38 H35 A340 L=370, drilling steel | Face drilling | 13468.95 | 9.7898 | 0.567% | 96.9% | No
14. Cable bolt twin strand bulbed 15.2 mm | Cable bolting | 10006.5782 | 7.2732 | 0.4213% | 97.32% | No
15. T38 extension round rod L=3050 mm | Face drilling | 9840.33 | 7.1523 | 0.4143% | 97.73% | No
16. A340 45 mm button bit | Face drilling | 8445.51 | 6.1385 | 0.3556% | 98.09% | No
17. A340 43 mm button bit | Face drilling | 8315 | 6.0437 | 0.3501% | 98.44% | No
18. T38 64 mm button bit | Face drilling | 7504.2 | 5.4544 | 0.3159% | 98.75% | No
19. Boring centraliser dia 48 mm | Face drilling | 5201.01 | 3.7803 | 0.219% | 98.97% | No
20. A340 51 mm retrac bit | Face drilling | 4706.5 | 3.4209 | 0.1981% | 99.17% | No
21. MF rod T38 R39 L=3050 mm | Face drilling | 4395.9 | 3.1951 | 0.1851% | 99.36% | No
22. A340 48 mm TC button bit | Face drilling | 3786.65 | 2.7523 | 0.1594% | 99.51% | No
23. Friction bolt 39 x 900 galvanised | Ground support | 3249.1776 | 2.3616 | 0.1368% | 99.65% | No
24. Bolting centraliser dia 66 mm guide | Face drilling | 2752.58 | 2.0007 | 0.1159% | 99.77% | No
25. Bolting centraliser dia 70 mm front | Face drilling | 1128 | 0.81988 | 0.04749% | 99.82% | No
26. Extension rod T38 R39 L=915 mm | Face drilling | 1108.5 | 0.8057 | 0.04667% | 99.86% | No
27. MF rod T38 R39 L=915 mm | Face drilling | 829.89 | 0.6032 | 0.03494% | 99.9% | No
28. T38 dolly 47 mm | Face drilling | 770.4 | 0.55996 | 0.03243% | 99.93% | No
29. Coupling sleeve T38 / T38 | Face drilling | 629.64 | 0.45765 | 0.02651% | 99.96% | No
30. T38 dolly 39 mm | Face drilling | 481.5 | 0.34997 | 0.02027% | 99.98% | No
31. Boring centraliser dia 48 mm | Face drilling | 366.54 | 0.26642 | 0.01543% | 99.99% | No
32. Bolting centraliser dia 70 mm back | Face drilling | 204 | 0.14828 | 0.008588% | 100% | No
Total |  | 2375287.2314 | 1726.4545 |  | 100%
Yes marks every item needed to reach 80 per cent of cumulative cost.
See Notes sheet, note 16.

## Triangulation
RECONCILIATION OF CONSUMPTION ACROSS THE THREE MINE RECORDS
Source: EOM stock counts, LiveMine installation records and Stock Usage issue registers, May to August 2026.
No record has been adjusted to match another. Where they disagree, the disagreement is the finding.
1 WHAT EACH RECORD ACTUALLY MEASURES
Record | Measures | What it captures |  |  | Typically
Stock count | Left the store | Everything drawn out of store between two counts, whether installed, broken, lost or still on the stockpile |  |  | Highest
LiveMine | Went into the rock | Material the operator recorded as installed, by shift and heading |  |  | Middle
Issue register | Signed for | Only transactions written on a docket. Bulk drops and untracked draws are missed |  |  | Lowest
See Notes sheet, note 17.
2 THE THREE RECORDS COMPARED
Consumable | Month | Stock count | LiveMine | Issue register | Costed in this model | Spread, highest over lowest | Bought but not installed | Comment
MD bolt 2.4 m | May | 2575 | 2956 | 1852 | 2575 | 1.5961 | -381 | Consistent
MD bolt 2.4 m | June | 3674 | 3191 | 885 | 3674 | 4.1514 | 483 | Consistent
MD bolt 2.4 m | July | 4163 | 3961 | 1602 | 4163 | 2.5986 | 202 | Consistent
MD bolt 2.4 m | August | 3319 | not supplied | 4339 | 3319 | n/a
Friction bolt 47 x 2400 | May | 743 | 1025 | 156 | 743 | 6.5705 | -282 | Investigate
Friction bolt 47 x 2400 | June | 949 | 671 | 1350 | 949 | 2.0119 | 278 | Investigate
Friction bolt 47 x 2400 | July | 2159 | 2114 | 728 | 2159 | 2.9657 | 45 | Consistent
Friction bolt 47 x 2400 | August | 2286 | not supplied | 2234 | 2286 | n/a
Friction bolt 47 x 900 | May | 300 | 78 | 26 | 300 | 11.5385 | 222 | Investigate
Friction bolt 47 x 900 | June | 529 | 345 | 150 | 529 | 3.5267 | 184 | Investigate
Friction bolt 47 x 900 | July | 401 | 293 | 270 | 401 | 1.4852 | 108 | Investigate
Friction bolt 47 x 900 | August | 320 | not supplied | 446 | 320 | n/a
Friction bolt 39 x 900 | May | 183 | 6 | 0 | 183 | n/a | 177 | Investigate
Friction bolt 39 x 900 | June | 177 | 37 | 0 | 177 | n/a | 140 | Investigate
Friction bolt 39 x 900 | July | 0 | 5 | 150 | 0 | n/a | -5
Friction bolt 39 x 900 | August | 80 | not supplied | 150 | 80 | n/a
Mesh 2.40 x 4.50 m | May | 2291 | 396 | 200 | 2291 | 11.455 | 1895 | Investigate
Mesh 2.40 x 4.50 m | June | 408 | 483 | 230 | 408 | 2.1 | -75 | Consistent
Mesh 2.40 x 4.50 m | July | 821 | 676 | 369 | 821 | 2.2249 | 145 | Consistent
Mesh 2.40 x 4.50 m | August | 769 | not supplied | 799 | 769 | n/a
Cable bolt | May | 27 | 0 | 0 | 27 | n/a | 27 | Investigate
Cable bolt | June | 0 | 66 | 51 | 0 | n/a | -66
Cable bolt | July | 60 | 40 | 18 | 60 | 3.3333 | 20 | Investigate
Cable bolt | August | 60 | not supplied | 69 | 60 | n/a
Total, all items, May to August |  | 26294 | 16343 | 16074 | 26294 |  | 3117
3 WHAT THE GAP MEANS, FOR THE MONTHS WHERE LIVEMINE WAS SUPPLIED
Measure |  | Units |  |  | Share of stock count |  |  | Meaning
Left the store, by stock count |  | 19460 |  |  | 100% |  |  | The mine paid for all of this
Went into the rock, by LiveMine |  | 16343 |  |  | 83.98% |  |  | This is what the ground actually received
Difference, bought but not installed |  | 3117 |  |  | 16.02% |  |  | Breakage, loss, and stock still lying at the portal
See Notes sheet, note 18.
4 THE SAME GAP IN MONEY
Measure |  | Cost (US$), May to July |  |  | US$ per metre advanced |  |  | Meaning
Ground support cost as costed, on the stock count |  | 1062068.8203 |  |  | 1078.4056 |  |  | The months where an installation record exists
Ground support cost of the material actually installed |  | 891952.2472 |  |  | 905.6723 |  |  | Scaled by the installed share above. It is an estimate, not a separate costing
Cost of material bought but not installed |  | 170116.5731 |  |  | 172.7333 |  |  | The size of the prize if the loss is closed
See Notes sheet, note 19.
5 CHART DATA
Record | Units, period
Stock count | 26294
LiveMine | 16343
Issue register | 16074

## May_Question
WHY MAY SHOWS LOW METRES AND A HIGH CONSUMPTION RATE
Question raised by the mine manager. Every figure below is calculated on this sheet from the same sources as the rest of the workbook.
1 THE TWO FIGURES THE QUESTION IS ABOUT
Measure | Unit | May | June | July | August | Period | Rank of May
Metres advanced | m | 270.436 | 316.617 | 397.798 | 390.967 | 1375.818 |  | Lowest of the four months
Total consumable cost | US$ | 553444.3884 | 463281.7783 | 736352.8137 | 622208.2511 | 2375287.2314
Consumable cost per metre, as counted | US$ / m | 2046.4893 | 1463.2246 | 1851.0722 | 1591.4598 | 1726.4545 |  | Highest of the four months
See Notes sheet, note 20.
2 IS THE MAY CONSUMPTION REAL? THE MESH TEST
Record | Unit | May | June | July | August |  | What it measures
Mesh sheets, stock count | sheets | 2291 | 408 | 821 | 769 |  |  | Everything that left the store
Mesh sheets, LiveMine installed | sheets | 396 | 483 | 676 | not supplied |  |  | What the operator recorded as installed
Sheets per metre advanced | Unit | May | June | July | August |  | Comparison
From the stock count | sheets / m | 8.4715 | 1.2886 | 2.0639 | 1.9669 |  |  | May is four to six times every other month
From LiveMine | sheets / m | 1.4643 | 1.5255 | 1.6994 |  |  |  | May sits with June, July and the design
Design standard, both GSS drawings | sheets / m | 1.5 | 1.5 | 1.5 | 1.5 |  |  | 6 sheets per 4.0 m cut
See Notes sheet, note 21.
3 THE SIZE OF THE COUNTING ERROR
Measure | Unit | Value |  |  |  |  | Basis
Mesh sheets counted as used in May | sheets | 2291 | [5 empty] | End of month stock reconciliation
Mesh sheets recorded as installed in May | sheets | 396 | [5 empty] | LiveMine installation record
Sheets counted but not installed | sheets | 1895 | [5 empty] | The difference between the two rows above
Unit cost of one mesh sheet | US$ | 82.4854 | [5 empty] | Mine price list, converted at the rate on Inputs
Value of the overstatement | US$ | 156309.8534 | [5 empty] | Sheets counted but not installed, multiplied by the unit cost
4 MAY WITH THE COUNTING ERROR REMOVED
Measure | Unit | May 2026 |  |  |  |  | Comment
Consumable cost per metre, as counted | US$ / m | 2046.4893 | [5 empty] | The figure the question is about
Less the mesh overstatement, per metre | US$ / m | 577.992 | [5 empty] | The counting error expressed per metre advanced
Consumable cost per metre, corrected | US$ / m | 1468.4973 | [5 empty] | May on the same basis as the other three months
Mean of June, July and August | US$ / m | 1635.2522 | [5 empty] | The three months with no known counting error
Corrected May against that mean | US$ / m | -166.7549 | [5 empty] | Negative means May was cheaper per metre than the other months
See Notes sheet, note 22.
5 ANSWER IN ONE LINE
May did not have a high consumption rate. One mesh stock count was overstated, and that single error accounts for the whole difference.
See Notes sheet, note 23.

## Charts
FIGURES
Each figure is followed by the table of values it was drawn from.
Figure 1. Ground support consumable cost per metre, by month
Values used in Figure 1
Month | US$ per metre
May | 1395.9165
June | 944.1671
July | 969.395
August | 837.1607
Figure 2. Development advance, by month
Values used in Figure 2
Month | Metres advanced
May | 270.436
June | 316.617
July | 397.798
August | 390.967
Figure 3. Total consumable cost, ten largest items, May to August 2026
Values used in Figure 3
Consumable | Total cost (US$)
MD bolt 2.4 m | 904575.3161
Shank T45 | 473326.75
Mesh 2.4 x 4.5 m | 353779.9267
Bit adaptor T45/T38 | 227125.95
Coupling T45/T38 | 100124.44
Friction bolt 47x2400 | 97769.3141
Speed rod T38 | 46647
Friction bolt 47x900 | 19990.6987
Boring centraliser 41 | 18848.3
Shank T38 | 16021.2
Figure 4. Share of total consumable cost, ten largest items
Values used in Figure 4
Consumable | Share of total cost
MD bolt 2.4 m | 38.08%
Shank T45 | 19.93%
Mesh 2.4 x 4.5 m | 14.89%
Bit adaptor T45/T38 | 9.562%
Coupling T45/T38 | 4.215%
Friction bolt 47x2400 | 4.116%
Speed rod T38 | 1.964%
Friction bolt 47x900 | 0.8416%
Boring centraliser 41 | 0.7935%
Shank T38 | 0.6745%
Figure 5. Bolts installed per metre advanced
Values used in Figure 5
Month | Bolts per metre
May | 14.0551
June | 16.8311
July | 16.9005
August | 15.3594
Figure 6. Mesh sheets installed per metre advanced
Values used in Figure 6
Month | Mesh sheets per metre
May | 8.4715
June | 1.2886
July | 2.0639
August | 1.9669
Figure 7. Consumption recorded by each measure, May to July 2026
Values used in Figure 7
Measure | Units
Stock count | 34961
Issue register | 17102
Figure 8. Metres driven in each ground class, May to August 2026
Values used in Figure 8
Ground class | Metres
GSS_01 good | 152.678
GSS_02 fair | 238.289
GSS_03 poor | 0
Figure 9. Cost per metre by portal, May to August 2026
Values used in Figure 9
Portal | US$ per metre
Northern Portal | 1036.7869
Southern Portal | 976.9591
Figure 10. Development advance by heading, the eight largest
Values used in Figure 10
Heading | Metres advanced
North Decline | 95.452
South Decline | 66.894
North Shoot Decline (NS_1040_ACC_N) | 31.787
MS900_DDR_N | 0
NS_1020_ACC_W | 57.558
MS_0900_RAD_E | 0
MS_900_RAD_E | 32.861
NS_1020_RAD_N | 32.709

## Daily_Log
DAILY LOG
Source: LiveMine daily records, 1 May to 24 August 2026. One row per day.
Rows to 24 August are loaded from LiveMine. Continue below in the same format, one row per day.
Date | Shift | Portal | Heading | Ground class | Advance (m) | MD bolts installed | Split sets installed | Mesh sheets installed | Holes drilled | Rods changed | Items returned serviceable | Source or remark
2026-05-01 |  |  |  |  | 8 | 70 | 11 | 13 | 146 |  |  | LiveMine
2026-05-02 |  |  |  |  | 8 | 74 | 27 | 6 | 100 |  |  | LiveMine
2026-05-03 |  |  |  |  | 8 | 90 | 25 | 15 | 155 |  |  | LiveMine
2026-05-04 |  |  |  |  | 8 | 49 | 11 | 4 | 123 |  |  | LiveMine
2026-05-05 |  |  |  |  | 4 | 63 | 14 | 9 | 78 |  |  | LiveMine
2026-05-06 |  |  |  |  | 8 | 85 | 66 | 18 | 149 |  |  | LiveMine
2026-05-07 |  |  |  |  | 4 | 97 | 37 | 16 | 89 |  |  | LiveMine
2026-05-08 |  |  |  |  | 8 | 45 | 13 | 6 | 118 |  |  | LiveMine
2026-05-09 |  |  |  |  | 20 | 113 | 53 | 16 | 195 |  |  | LiveMine
2026-05-10 |  |  |  |  | 8 | 63 | 54 | 6 | 95 |  |  | LiveMine
2026-05-11 |  |  |  |  | 8 | 59 | 54 | 9 | 145 |  |  | LiveMine
2026-05-12 |  |  |  |  | 4 | 82 | 15 | 12 | 78 |  |  | LiveMine
2026-05-13 |  |  |  |  | 8 | 79 | 44 | 15 | 182 |  |  | LiveMine
2026-05-14 |  |  |  |  | 12 | 110 | 62 | 11 | 233 |  |  | LiveMine
2026-05-15 |  |  |  |  | 4 | 83 | 49 | 5 | 65 |  |  | LiveMine
2026-05-16 |  |  |  |  | 4 | 42 | 11 | 8 | 62 |  |  | LiveMine
2026-05-17 |  |  |  |  | 4 | 58 | 14 | 9 | 73 |  |  | LiveMine
2026-05-18 |  |  |  |  | 8 | 71 | 76 | 11 | 153 |  |  | LiveMine
2026-05-19 |  |  |  |  | 12 | 197 | 49 | 26 | 240 |  |  | LiveMine
2026-05-20 |  |  |  |  | 10.5 | 125 | 37 | 20 | 196 |  |  | LiveMine
2026-05-21 |  |  |  |  | 15.5 | 129 | 34 | 14 | 284 |  |  | LiveMine
2026-05-22 |  |  |  |  | 4 | 88 | 23 | 5 | 87 |  |  | LiveMine
2026-05-23 |  |  |  |  | 20 | 172 | 52 | 18 | 371 |  |  | LiveMine
2026-05-24 |  |  |  |  | 12 | 129 | 41 | 14 | 180 |  |  | LiveMine
2026-05-25 |  |  |  |  | 12 | 114 | 26 | 15 | 246 |  |  | LiveMine
2026-05-26 |  |  |  |  | 8 | 193 | 33 | 31 | 158 |  |  | LiveMine
2026-05-27 |  |  |  |  | 12 | 111 | 38 | 12 | 248 |  |  | LiveMine
2026-05-28 |  |  |  |  | 8.2 | 144 | 26 | 21 | 155 |  |  | LiveMine
2026-05-29 |  |  |  |  | 12.2 | 103 | 47 | 19 | 224 |  |  | LiveMine
2026-05-30 |  |  |  |  | 4.2 | 55 | 33 | 5 | 71 |  |  | LiveMine
2026-05-31 |  |  |  |  | 8 | 63 | 34 | 7 | 140 |  |  | LiveMine
2026-06-01 |  |  |  |  | 12 | 167 | 0 | 25 | 243 |  |  | LiveMine
2026-06-02 |  |  |  |  | 12 | 108 | 27 | 13 | 279 |  |  | LiveMine
2026-06-03 |  |  |  |  | 12 | 147 | 29 | 15 | 249 |  |  | LiveMine
2026-06-04 |  |  |  |  | 8 | 127 | 43 | 20 | 175 |  |  | LiveMine
2026-06-05 |  |  |  |  | 8 | 27 | 23 | 6 | 142 |  |  | LiveMine
2026-06-06 |  |  |  |  | 8 | 114 | 62 | 21 | 175 |  |  | LiveMine
2026-06-07 |  |  |  |  | 8 | 81 | 32 | 13 | 148 |  |  | LiveMine
2026-06-08 |  |  |  |  | 8 | 213 | 57 | 34 | 148 |  |  | LiveMine
2026-06-09 |  |  |  |  | 8 | 168 | 98 | 29 | 158 |  |  | LiveMine
2026-06-10 |  |  |  |  | 16 | 42 | 55 | 6 | 306 |  |  | LiveMine
2026-06-11 |  |  |  |  | 8 | 91 | 34 | 17 | 154 |  |  | LiveMine
2026-06-12 |  |  |  |  | 12 | 132 | 57 | 23 | 227 |  |  | LiveMine
2026-06-13 |  |  |  |  | 8 | 170 | 51 | 28 | 166 |  |  | LiveMine
2026-06-14 |  |  |  |  | 18.5 | 104 | 34 | 10 | 316 |  |  | LiveMine
2026-06-15 |  |  |  |  | 8 | 105 | 25 | 19 | 123 |  |  | LiveMine
2026-06-16 |  |  |  |  | 12 | 104 | 21 | 7 | 233 |  |  | LiveMine
2026-06-17 |  |  |  |  | 4 | 92 | 24 | 13 | 70 |  |  | LiveMine
2026-06-18 |  |  |  |  | 8 | 66 | 14 | 10 | 144 |  |  | LiveMine
2026-06-19 |  |  |  |  | 20 | 127 | 30 | 14 | 269 |  |  | LiveMine
2026-06-20 |  |  |  |  | 16 | 212 | 28 | 28 | 127 |  |  | LiveMine
2026-06-21 |  |  |  |  | 12 | 49 | 44 | 7 | 143 |  |  | LiveMine
2026-06-22 |  |  |  |  | 4 | 30 | 30 | 7 | 46 |  |  | LiveMine
2026-06-23 |  |  |  |  | 8 | 50 | 14 | 11 | 0 |  |  | LiveMine
2026-06-24 |  |  |  |  | 15.5 | 72 | 30 | 16 | 232 |  |  | LiveMine
2026-06-25 |  |  |  |  | 8 | 126 | 38 | 12 | 178 |  |  | LiveMine
2026-06-26 |  |  |  |  | 4 | 94 | 12 | 17 | 68 |  |  | LiveMine
2026-06-27 |  |  |  |  | 24 | 107 | 56 | 14 | 186 |  |  | LiveMine
2026-06-28 |  |  |  |  | 8 | 91 | 43 | 16 | 58 |  |  | LiveMine
2026-06-29 |  |  |  |  | 10.5 | 65 | 24 | 9 | 225 |  |  | LiveMine
2026-06-30 |  |  |  |  | 8 | 110 | 18 | 23 | 160 |  |  | LiveMine
2026-07-01 |  |  |  |  | 12 | 185 | 39 | 23 | 219 |  |  | LiveMine
2026-07-02 |  |  |  |  | 20 | 58 | 50 | 7 | 327 |  |  | LiveMine
2026-07-03 |  |  |  |  | 12 | 42 | 39 | 7 | 276 |  |  | LiveMine
2026-07-04 |  |  |  |  | 4 | 80 | 19 | 15 | 155 |  |  | LiveMine
2026-07-05 |  |  |  |  | 12 | 191 | 119 | 34 | 245 |  |  | LiveMine
2026-07-06 |  |  |  |  | 16 | 124 | 64 | 17 | 307 |  |  | LiveMine
2026-07-07 |  |  |  |  | 12 | 127 | 39 | 16 | 240 |  |  | LiveMine
2026-07-08 |  |  |  |  | 8 | 140 | 82 | 25 | 155 |  |  | LiveMine
2026-07-09 |  |  |  |  | 12 | 171 | 62 | 24 | 231 |  |  | LiveMine
2026-07-10 |  |  |  |  | 12 | 80 | 91 | 16 | 231 |  |  | LiveMine
2026-07-11 |  |  |  |  | 16 | 111 | 85 | 22 | 331 |  |  | LiveMine
2026-07-12 |  |  |  |  | 16 | 167 | 118 | 32 | 282 |  |  | LiveMine
2026-07-13 |  |  |  |  | 12 | 68 | 57 | 11 | 224 |  |  | LiveMine
2026-07-14 |  |  |  |  | 12 | 119 | 78 | 16 | 301 |  |  | LiveMine
2026-07-15 |  |  |  |  | 12 | 206 | 113 | 30 | 310 |  |  | LiveMine
2026-07-16 |  |  |  |  | 24 | 118 | 78 | 22 | 381 |  |  | LiveMine
2026-07-17 |  |  |  |  | 8 | 86 | 41 | 19 | 158 |  |  | LiveMine
2026-07-18 |  |  |  |  | 16 | 118 | 74 | 18 | 241 |  |  | LiveMine
2026-07-19 |  |  |  |  | 20 | 164 | 112 | 24 | 311 |  |  | LiveMine
2026-07-20 |  |  |  |  | 16 | 162 | 96 | 28 | 366 |  |  | LiveMine
2026-07-21 |  |  |  |  | 12 | 130 | 117 | 23 | 178 |  |  | LiveMine
2026-07-22 |  |  |  |  | 14.5 | 98 | 40 | 15 | 255 |  |  | LiveMine
2026-07-23 |  |  |  |  | 16 | 160 | 106 | 28 | 309 |  |  | LiveMine
2026-07-24 |  |  |  |  | 20 | 209 | 79 | 38 | 295 |  |  | LiveMine
2026-07-25 |  |  |  |  | 16 | 124 | 98 | 24 | 314 |  |  | LiveMine
2026-07-26 |  |  |  |  | 6.5 | 93 | 62 | 17 | 163 |  |  | LiveMine
2026-07-27 |  |  |  |  | 8 | 127 | 84 | 29 | 176 |  |  | LiveMine
2026-07-28 |  |  |  |  | 0 | 134 | 85 | 18 | 66 |  |  | LiveMine
2026-07-29 |  |  |  |  | 8 | 104 | 74 | 22 | 232 |  |  | LiveMine
2026-07-30 |  |  |  |  | 16 | 99 | 66 | 25 | 167 |  |  | LiveMine
2026-07-31 |  |  |  |  | 12 | 166 | 145 | 31 | 327 |  |  | LiveMine
2026-08-01 |  |  |  |  | 8 | 91 | 59 | 22 | 168 |  |  | LiveMine
2026-08-02 |  |  |  |  | 13 | 77 | 58 | 9 | 258 |  |  | LiveMine
2026-08-03 |  |  |  |  | 8 | 156 | 77 | 28 | 125 |  |  | LiveMine
2026-08-04 |  |  |  |  | 16 | 125 | 49 | 22 | 302 |  |  | LiveMine
2026-08-05 |  |  |  |  | 20 | 100 | 62 | 19 | 270 |  |  | LiveMine
2026-08-06 |  |  |  |  | 20 | 207 | 108 | 39 | 358 |  |  | LiveMine
2026-08-07 |  |  |  |  | 8 | 93 | 47 | 16 | 163 |  |  | LiveMine
2026-08-08 |  |  |  |  | 20 | 141 | 123 | 22 | 362 |  |  | LiveMine
2026-08-09 |  |  |  |  | 8 | 33 | 16 | 5 | 172 |  |  | LiveMine
2026-08-10 |  |  |  |  | 12 | 115 | 54 | 21 | 166 |  |  | LiveMine
2026-08-11 |  |  |  |  | 16 | 145 | 72 | 28 | 224 |  |  | LiveMine
2026-08-12 |  |  |  |  | 16 | 143 | 92 | 24 | 289 |  |  | LiveMine
2026-08-13 |  |  |  |  | 10.5 | 107 | 83 | 20 | 211 |  |  | LiveMine
2026-08-14 |  |  |  |  | 8 | 49 | 39 | 6 | 225 |  |  | LiveMine
2026-08-15 |  |  |  |  | 8 | 87 | 55 | 20 | 103 |  |  | LiveMine
2026-08-16 |  |  |  |  | 14.5 | 185 | 113 | 27 | 235 |  |  | LiveMine
2026-08-17 |  |  |  |  | 18.5 | 33 | 31 | 7 | 373 |  |  | LiveMine
2026-08-18 |  |  |  |  | 4 | 104 | 71 | 21 | 64 |  |  | LiveMine
2026-08-19 |  |  |  |  | 20 | 99 | 67 | 21 | 376 |  |  | LiveMine
2026-08-20 |  |  |  |  | 8 | 132 | 64 | 25 | 82 |  |  | LiveMine
2026-08-21 |  |  |  |  | 16 | 145 | 101 | 28 | 301 |  |  | LiveMine
2026-08-22 |  |  |  |  | 12.4 | 85 | 36 | 14 | 174 |  |  | LiveMine
2026-08-23 |  |  |  |  | 8.2 | 0 | 0 | 0 | 146 |  |  | LiveMine
2026-08-24 |  |  |  |  | 6.5 | 0 | 0 | 0 | 132 |  |  | LiveMine
2026-08-25 |  |  |  |  | 12 | 0 | 0 | 0 | 178 |  |  | LiveMine
2026-08-26 |  |  |  |  | 10.5 | 0 | 0 | 0 | 213 |  |  | LiveMine
2026-08-27 |  |  |  |  | 12 | 0 | 0 | 0 | 305 |  |  | LiveMine
2026-08-28 |  |  |  |  | 12 | 0 | 0 | 0 | 234 |  |  | LiveMine
2026-08-29 |  |  |  |  | 16 | 0 | 0 | 0 | 239 |  |  | LiveMine
2026-08-30 |  |  |  |  | 4 | 0 | 0 | 0 | 84 |  |  | LiveMine

## Daily_Tracker
DAILY TRACKER
Reads the Daily Log. Compares what is happening now against the May to July baseline.
The tracker measures material installed, not material issued. See the Dashboard for why those differ.
1 BASELINE, MEASURED MAY TO JULY 2026
Measure | Unit | Mean | Standard deviation | Lower limit | Upper limit | Basis
Bolts installed per metre | bolts/m | 15.9289 | 1.6231 | 12.6826 | 19.1752 |  | May to July figures, all bolt types
Mesh sheets per metre | sheets/m | 1.6762 | 0.38762 | 0.901 | 2.4515 |  | June and July only, May count is unreliable
Advance rate | m/day | 10.7324 | 2.3122 | 6.108 | 15.3568 |  | Survey metres divided by days in period
See Notes sheet, note 24.
2 RUNNING TOTALS FROM THE DAILY LOG
Measure | Unit | Value |  |  |  |  | Against baseline
Shifts logged | shifts | 121
Metres advanced | m | 1350.2
MD bolts installed | units | 12490
Split sets installed | units | 6040
Mesh sheets installed | units | 1986
Items returned serviceable | units | 0
Bolts per metre, actual | per m | 13.7239 |  |  |  | Within the normal range
Mesh sheets per metre, actual | per m | 1.4709 |  |  |  | Within the normal range
3 BY DAY
Date | Shifts | Metres advanced | MD bolts | Split sets | Mesh sheets |  | Bolts per metre
Type a date in the first column and the row fills itself from the Daily Log.

## Anomalies
DATA QUERIES AND ITEMS FOR CONFIRMATION
Queries raised against the source records during the analysis, with the effect of each on the result.
No. | Item | Observation | Effect on the result | Status | Action required
1 | May mesh count | The May stock count says 2,291 sheets. LiveMine says 396, the issue register 200, and the design 1.5 per metre. June, July and August all sit between 1.3 and 2.1 per metre; May would need 8.5. | 1,895 sheets, US$156,310 of May cost | Resolved, the count is wrong | Recount, or accept the LiveMine figure of 396 which three records support. Worked through on the May_Question sheet.
2 | Support standard read off the drawings | The GSS01 and GSS02 drawings give 33 and 15 MD bolts per cut, 0 and 18 split sets of 2.4 m, 11 stubby split sets, and 6 mesh sheets. Earlier design figures used in this model were not taken from the drawings. | Changes every design variance in the model | Resolved | Design quantities now read directly off the two approved drawings, split by bolt type.
3 | Stubby split sets below the drawing quantity | Both drawings call for 11 stubby 0.9 m split sets per cut. Consumption runs at 0.0 to 0.7 per metre against a drawing quantity of 2.75. The 0.9 m x 47 mm friction bolt, which has no line on either drawing, runs at 1.13 per metre. | 75 to 100 per cent below, every month | Open, for ground control | Ask ground control and the shift bosses why the stubby is not reaching the face, and whether the 47 mm 0.9 m bolt is being used in its place.
4 | Long bolts above the drawing quantity | MD bolts run 37 to 102 per cent above and 2.4 m split sets 20 to 113 per cent above. Note that the drawings state a MINIMUM quantity per cut, so installing above it is compliance rather than over consumption. | Long bolt excess is 2.55 times the stubby shortfall, so substitution explains at most 39 per cent of it | Open, for ground control | Confirm whether the extra support was required by ground conditions. Quantity of ground support is a geotechnical decision, not a cost decision.
5 | Cut length assumption | Design per metre is the quantity per cut divided by the cut length. The 4.0 m cut is an entered value, not a measured one. | The MD bolt variance falls from 72 to 29 per cent between a 4.0 m and a 3.0 m cut | Open | Measure the achieved cut length from the survey record. Until then quote the range on Plan_vs_Actual section 6, not the single figure.
6 | Three drilling prices | Shank T45 at 5,568.55 against 308.10 for the T38 equivalent. Coupling T45/T38 at 1,925.47 against 69.96. Boring centraliser 41 mm at 1,884.83 against 61.09 for the same part under a second supplier code. | 80 per cent of the drilling bill; the drilling unit cost ranges from US$717 to US$140 per metre | Blocking | Operations manager confirms whether these are per each, per box, or a currency error.
7 | August LiveMine inventory not supplied | The August extract contains the Jumbo PLOD but no inventory sheet, so August has no measured installation record. | August cannot be triangulated and its portal split falls back to metres | Open | Request the August inventory extract from LiveMine.
8 | July closing against August opening | Six items show a different closing count at the end of July from the opening count at the start of August, the largest being 484 MD bolts. | About 1 per cent of the period's bolts | Open, small | Confirm whether a recount or an unbooked issue took place between the two counts.
9 | Survey metres against PLOD metres | The survey claim and the LiveMine PLOD disagree on metres advanced. August is the widest, at 391.0 surveyed against 366.1 recorded. | Up to 6 per cent in a single month | Open, small | Survey remains the authority for metres in this model. Confirm the PLOD shortfall is unrecorded shifts.
10 | Friction bolt 39 x 900, July | Closing count 3,380 against opening 3,123 with no receipt booked. Stock grew without a delivery, so consumption computes to a negative 257. | One item, one month, held at zero | Open, small | Store confirms the unrecorded receipt.
11 | Portal and ground class confounded | The Northern Portal is driven entirely in GSS_02 and GSS_03 ground and the Southern Portal entirely in GSS_01, in all four months. | The two effects cannot be separated | Limitation | Note as a limitation of the study design. No further data from this period would resolve it.
12 | Stocktake and survey dates | Survey months run from the 29th to the 28th. Stock counts run to calendar month end. | Two to three days of consumption in the wrong month; no effect on period totals | Agreed fix | Align the stocktake date with the survey cut off.
13 | GSS_03 has no drawing | No drawing was issued for GSS_03. It appears only in July, in the Northern Portal, where GSS_02 also applies. | 217 of the 398 metres driven in July | Resolved | GSS_03 is benchmarked against the GSS_02 standard. Confirm this with ground control.
14 | Locations with no parent heading | The Southern Portal occupies levels 840 to 940 and the Northern Portal levels 1020 and 1040, with no overlap, so a location can be assigned from its level number. | Nine locations resolved on this rule | Resolved | Rule applied. Four locations remain unassigned because they carry no level number.
15 | Four locations still unassigned | PMP_STN01 and Navachab carry no level. DSP_O6 and DSP_07 match a DSP heading in both portals. | Held out of the portal split, included in the mine total | Open, small | One question to survey on which decline each belongs to.

## Data_Quality
DATA QUALITY AND LIMITATIONS
Issues found in the source data and what is needed to resolve each one.
Severity | Affected data | Issue and effect | Action required
Critical | Drilling consumable prices | The unit cost file covers ground support only. No price exists for any bit, rod, shank or coupling. Drilling cost per metre shows x. Consumption is measured in full. | Obtain the Sandvik, DSI and Maspro price list. Enter it on C_Face_Drilling.
Critical | Fixed labour and machine cost | No labour or machine cost, and no shift count, appears in any supplied file. Equation 3 and the advance scenarios show y. | Obtain the fixed cost schedule and the shift count per month.
Critical | Consumption not recorded by heading | The stocktake is one count for the whole store. The issue register records only North Portal or South Portal. Cost per heading cannot be calculated. | Code stores issues to a heading. This is what the field recording sheets capture.
High | MS_1040_ACC, May 2026 | Southern prefix but Northern level number. 27.178 m affected. May is therefore excluded from the portal analysis. | Ask survey which side the 1040 access was driven from in May 2026.
High | May 2026 stock counts | The two May half month counts do not chain. 26 items disagree and 11 receipts appear twice. May mesh shows 8.47 sheets per metre against 1.29 in June, which is not physically achievable. | Confirm the 15 May count with stores. Treat May as provisional.
High | Friction bolt 39 x 900, July | Closing count exceeds opening plus receipts, giving minus 257 units. Held at zero in every calculation. | Locate the unrecorded receipt or recount.
High | Ground support standard changed | GSS_03 is absent in May and June, then covers 217 of 398 metres in July. This drives cost per metre directly. | Confirm with the geotechnician whether ground or classification changed.
High | Design support quantities | The GSS design drawings are not among the supplied files, so over consumption cannot be proved. | Obtain the GSS_01, GSS_02 and GSS_03 drawings.
Medium | Bolts per metre look high | 16.9 bolts per metre in July against an expected 9 to 12 for this profile. | Compare against the design standard once the drawings are obtained.
Medium | Heading naming across months | May uses a different naming convention from June and July, so no continuous heading series can be built. | Obtain the survey heading register.
Medium | Reporting periods differ | Survey months run 29th to 28th. Stock counts run to calendar month end. | Align the stocktake date with the survey cut off.
Medium | Stores item recoding | Friction bolt 47 x 2400 changes code between June and July. Codes are combined in this model. | Ask stores to keep one code per physical item.
Low | Shotcrete | A price exists but no volume appears in the stock records, so the shotcrete term is zero. | Confirm whether shotcrete was applied in the period.
Low | Cable bolt length | The item consumed is 6.5 m, the price list has 6 m only. Cable bolting is 0.6 per cent of cost. | Request the 6.5 m price.
Low | Barrel and wedge anchors | Consumed in all three months but no unit price is available. | Request the price from the supplier.

## How_to_Read
HOW TO READ THIS WORKBOOK
What each sheet contains, and what the symbols and formats mean.
SYMBOLS AND FORMATS
Symbol | Meaning
x | No unit price for this item exists in the source data. It is not zero and is never treated as zero.
y | An input that has not yet been collected. It is not zero and is never treated as zero.
- | The cost is already carried by another line. Repeating it here would double count.
Negative number | Shown with a minus sign. In the consumption sheets it means the closing stock count was higher than opening stock plus recorded receipts, which is a counting or receipting error, not negative usage.
Blue figures | Entered directly from a source document.
Green figures | Drawn from another sheet in this workbook.
Black figures | Calculated on this sheet.
Shaded cells | Awaiting data. Every one is listed on the Data_Quality sheet.
WHAT EACH SHEET CONTAINS
Sheet | Contents
Equations | Every equation used, with each symbol defined and the sheet it is calculated on.
Inputs | Unit costs, the exchange rate, the ground support design quantities and the drilling geometry. Everything the model needs that is not consumption or metres.
Advance | Survey advance exactly as recorded, then the monthly totals and advance rates.
Consumption_PL | Consumption measured by physical stock count: opening plus received less closing.
Consumption_Issues | Consumption measured by the stores issue registers: the sum of quantities signed out.
Consumption_Compare | The two measures side by side, with the gap between them.
A_Scaling to D_Cable_Bolting | One sheet per development activity. Quantities consumed, units per metre, cost and cost per metre for every item.
DRM | Drilled metres. Bolt hole metres are calculated from bolts installed. Face metres need the drilling geometry inputs.
Plan_vs_Actual | Design quantities from the GSS drawings against actual consumption, by ground class.
Unit_Cost | Equations 1, 2 and 3, the advance rate scenarios, and the split of why unit cost moved.
Portal_Analysis | Results by heading and by portal, with the reconciliation checks.
Pareto | Consumables ranked by cost, showing which few carry most of the spend.
Charts | Each figure, followed by the table of values it was drawn from.
Data_Quality | Every problem found in the source data and what is needed to resolve it.
CHECKING THE WORKBOOK BALANCES
Check | Where
Heading metres equal portal metres, and Northern plus Southern equals the mine total | Portal_Analysis, section 3. All four checks must read zero.
The two causes of a change in unit cost sum to the total change | Unit_Cost, last row of the final section. Must read zero.
The cumulative share reaches exactly 100 per cent | Pareto, final row.
Ground class metres equal total metres | Plan_vs_Actual, section 1 total.